Production Deployment Plan

AP/Relay NIC Firmware

Document Control

| CR / Project Number: |  |
| --- | --- |
| Version No: | 1.03 |
| Created On: | 04/06/2024 |
| Last Updated: |  |
| Status: |  |
| Author/s: | Percy Ahangama Arachchige |

Approval Status

| Stakeholder Role | Stakeholder Name | Signature | Date |
| --- | --- | --- | --- |
| Communication Networks Quality Manager | Leonard Jarillas |  |  |
| Communications Manager | Stuart Bannister |  |  |
| Meter Asset Manager | Goutham Lingam |  |  |
| IOT System Service Lead | Wilton Gao |  |  |

Document Purpose

The purpose of the Deployment Plan is to specify the business and technical resources, system requirements, steps and schedule for deployment. This document establishes the Go / No-Go criteria and the documentation requirements and gives final approval to go ahead as planned.

Related Documents

This section will list related documents. Please note that if this document is updated these related documents may also need to be changed.

| Document | Location | Relationship |
| --- | --- | --- |
| AP/Relay NIC Firmware – Test Summary Report |  | TSR |
| Functional Test Plan – AP_Relay Firmware 5.4.3.docx |  |  |

Reviewers

List the relevant reviewers who are responsible for the deliverables defined in this document.

| Reviewer Title | Reviewer Name | Reviewed (Yes/No) |
| --- | --- | --- |
| Metering Engineer • United Energy | Karl Ngo |  |
| Senior AMI Strategy Engineer • United Energy | Graeme Watson |  |
| AMI Communications Analyst • Network | Sangsukdee, Wayne |  |
| Communication Networks Laboratory Techni • Network | Njuguna, Kamau |  |
| AMI Communications Analyst • United Energy | Cherian, Jogy |  |

Document Distribution (Information only)

| Distributed to |  |
| --- | --- |

Table of Contents

1.	Introduction	4

1.1.	Project Background	4

1.2.	Objectives	4

1.3.	Dependencies	4

2.	Deployment Approach	5

2.1.	Scope	5

2.2.	Deployment Schedule and Stages	6

2.2.1.	Deployment Schedule	6

2.2.2.	Deployment Stages	8

1.	Pre-analysis Stage	9

2.	BVT Stage (10 Access points and 10 Relays)	9

3.	Stage 1 (100 Access points and 100 Relays)	10

4.	Stage 2 (300 Access points and 1000 relays)	12

5.	Stage 3 (All Access points and relays)	13

6.	BAU Stage (All remaining Access Points and relays)	14

3.	Deployment Roles and Responsibilities	16

3.1.	Deployment Lead	16

3.2.	Go – No Go	16

3.3.	Escalation	17

3.4.	Stakeholder Communication	17

3.5.	Operational and Support Groups	17

4.	Identified Risks	18

5.	Appendix	19

5.1.	FWU Progress Report	19

6.	Revision	20

# Introduction

## Project Background

All Itron network devices (Access Points, Relays and NICs) within the AMI network run firmware known as UtilOS. This firmware processes information sent through the mesh radio interface and enables functionality such as the reading of interval data off meters. New versions of UtilOS are released to address defects or to add functionality. Due to issues found in currently deployed UtilOS version 5.4.40,it has been deemed necessary to upgrade to UtilOS version 5.4.43.

Prior to the deployment of UtilOS 5.4.3 for GEN 5 APs/Relays, GEN 4.5 Relays and GEN 1.5 Relays into the production AMI system it is important to ensure that the introduction of this new release poses minimal risk to the business and that it meets the applicable requirements. To achieve this, the Communication Networks Quality Group carried out testing to ensure correct functionality.

It is recommended that UtilOS 5.4.3 firmware for GEN 5 APs/Relays, GEN 4.5 Relays and GEN 1.5 Relays can be deployed within the AMI Network with minimal risk to the business.

## Objectives

- Upgrade all Gen5 Access points NIC firmware 5.4.6043

- Upgarde all Gen 5 Relays NIC Firmware 5.4.6043

- Upgarde all Gen 4.5 Relays NIC Firmware 5.4.6023

- Upgarde all Gen 1.5 Relays NIC Firmware 5.4.5003

- Identify AP/Relays that cannot be upgraded and take action on them, if necessary.

## Dependencies

- AP/Relay NIC Firmware – Test certificateUtilOS_5-4-43-20240514

# Deployment Approach

## Scope

- Access points and relays with the following properties will be in scope of this deployment activity.

| Device type | Generation | NIC Architecture | Currently running NIC Firmware | New NIC firmware |
| --- | --- | --- | --- | --- |
| Access point | Gen 5 | RNI | 4.8.6002 | 5.4.6043 |
|  |  |  | 5.4.6040 |  |
| Relay | Gen 5 | RNI | 6.8.6002 | 5.4.6043 |
|  | Gen 4.5 | AKIO | 3.12.6009 | 5.4.6023 |
|  | Gen 1.5 | ARM | 3.12.5009 | 5.4.5003 |

Table 1: Device Firmware in Scope

- As of writing this document, there are 1072 Access points and 4354 Relays in the field that needs to be upgraded to NIC 5.4.6043.

| Current AP NIC version | Count of Device |
| --- | --- |
| 4.8.6002 | 437 |
| 5.4.6040 | 635 |
| Grand Total | 1072 |

Table 2: AP5 in Scope

| Current Relay NIC Version | Count of Device |
| --- | --- |
| 3.12.5009 | 4303 |
| 3.12.6009 | 43 |
| 4.8.6002 | 8 |
| Grand Total | 4354 |

Table 3: Relays in Scope

## Deployment Schedule and Stages

The upgrade of the Access points shall be prioritised.

The upgrade shall be divided into several stages as shown in the figure below

Deployment Schedule

The proposed deployment schedule is shown in the figure below in reference to the start date of 1st of july, 2024. This start date is dependent on the approval of the deployment plan (this document) The duration are estimates based on previous Ap/Relay firmware upgrades and will be monitored and adjusted during the deployment activity.

Figure 1- Deployment Schedule

Deployment Stages

The upgrade of the Access points shall be prioritised. After completing AP NIC upgrades, Relays will use the same deployment stages with different device counts.

The upgrade shall be divided into several stages as shown in the figure below:

BVT

(10APs)

Stage 1

(100 Aps)

Stage 2

(300 Aps)

Stage 3

(All remaining Aps)

BAU

(All APS)

Pre-analysis

- Identify APs for BVT, Stage 1 and Stage 2

- Upgrade to 10 Access points

- Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to 100 Access points

- Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to 300 Access Points

- Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to all Access points.

- BAU process Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to remaining  Access Points

- BAU process Check if any AP performances /malfunctions is introduced due to firmware upgrade.

Figure 2 - Firmware deployment stages

Progress of the firmware upgrade shall be monitored through the FWU reporting tool and FWU project details.

### Pre-analysis Stage

Resources Required: ACCG

The pre-analysis stage shall be composed of the following activities:

- Identify Access points with good communication history and avoid using COMMS_FLAPPERS

- List all Access points that are to be in scope of BVT, Stage 1 and Stage 2 based on the following criteria:

  - Operation state : Active

  - Location : close proximity to Rooney St. depot and Ardeer depot

  - BVT Stage : 10 Access points and 10 Relays

  - Stage 1: 100 Access Point and 100 Relays

  - Stage 2: 300 Access points and 1000 relays

- Import list of Access points and relays to into the tracking spreadsheet located in:

- ACC Deployment\2024 - AP-Relay NIC Firmware Deployment

- Collect all pre upgrade data and record in the tracking spreadsheet. The pre and post firmware upgrade data shall be compared to ensure that the expected behaviour is observed.

| Data to be collected | Method | Expected |
| --- | --- | --- |
| Access points and relays communication | UIQ Ping Schedule/NC/MKT | AP/Relay have >99% comms performance |
| Access point device count | UIQ Schedule/NC | Access Point and relay performance as normal |
| Access point Read sucess | UIQ Schedule/NC | Access Point performance as normal |
| Access point and relay events | UIQ Schedule/NC | There are no unexpected AP/Relay events generated |
| Meter Performance | UIQ Schedule | Hourly meter read performance as expected |

Table 4 - Pre & Post Upgrade Data

### BVT Stage (10 Access points and 10 Relays)

Resources Required: ACCG, UIQ Support, Data Analytics, AMI Data (MDP)

During the BVT stage, a small number (10) of Access points and 10 Relays shall be upgraded and the impact of the upgrade analyzed. This minimises the the risk of meter malfunctions, if any, that may be introduced by the new firmware that has not been detected during testing.

Steps:

  - Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

| Basic Information |  |
| --- | --- |
| Name: | BVT - <Vendor> <AP/Relay Image Type> <Firmware> |
| Audit job: | - |
| Type: | <autofilled> |
| Version: | <autofilled> |
| Image: | Firmware Image |
| Upgrade Settings |  |
| Seed density: | 100% of nodes are seeds |
| Upload image chunk size: | 1,024 bytes |
| Upload request timeout: | 60 seconds |
| Command request timeout: | 30 seconds |
| Retry count: | 3 |
| Gateway Priority: | Medium |
| E-mail addresses: | - |
| Verification interval: | 600 seconds |
| Maximum number of verification attempts: | 10 |
| Post-run Options |  |
| Auto restart upgrade: | 3 times |
| Auto complete upgrade: | Disabled |

  - Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past AP firmware upgrades.

  - Collect all post upgrade data and record in the tracking spreadsheet.

  - Compare the pre and post upgrade data in the tracking spreadsheet and verify the impact of the deployment of new firmware to the Access point/relay  performance.

  - Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major adverse effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

  - If all issues, if any, has been resolved, proceed to the next stage.

  - Communicate results of the BVT, and if proceeding to the next stage, to the relevant stakeholders.

### Stage 1 (100 Access points and 100 Relays)

Resources Required: ACCG, UIQ Support or Data Analytics

In Stage 1, a larger number (100) of Access points and 100 Relays shall be upgraded and the impact of the upgrade analyzed.

Steps:

- Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

| Basic Information |  |
| --- | --- |
| Name: | Stage 1 - <Vendor> <AP/Relay Image Type> <Firmware> |
| Audit job: | - |
| Type: | <autofilled> |
| Version: | <autofilled> |
| Image: | Firware Image |
| Upgrade Settings |  |
| Seed density: | 100% of nodes are seeds |
| Upload image chunk size: | 1,024 bytes |
| Upload request timeout: | 60 seconds |
| Command request timeout: | 30 seconds |
| Retry count: | 3 |
| Gateway Priority: | Medium |
| E-mail addresses: | - |
| Verification interval: | 600 seconds |
| Maximum number of verification attempts: | 10 |
| Post-run Options |  |
| Auto restart upgrade: | 3 times |
| Auto complete upgrade: | Disabled |

- Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past meter firmware upgrades.

- Monitor for any Access point/Relay failed the upgrade and send a list to the Communication Networks Quality Manager for investigation and triage.

- Collect all post upgrade data and record in the tracking spreadsheet.

- Compare the pre and post upgrade data in the tracking spreadsheet and verify the impact of the deployment of new firmware to the Access point/Relay performance.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- If all issues, if any, has been resolved, proceed to the next stage.

- Communicate results of the Stage 1, and if proceeding to the next stage, to the relevant stakeholders.

### Stage 2 (300 Access points and 1000 relays)

Resources Required: ACCG, UIQ Support or Data Analytics

In Stage 2, a significant number (300) of Access pints and 1000 Relays shall be upgraded and the impact of the upgrade analyzed.

Steps:

- Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

| Basic Information |  |
| --- | --- |
| Name: | Stage 2 - <Vendor> <AP/Relay Image Type> <Firmware> |
| Audit job: | - |
| Type: | <autofilled> |
| Version: | <autofilled> |
| Image: | Firware Image |
| Upgrade Settings |  |
| Seed density: | 3% of nodes are seeds |
| Upload image chunk size: | 1,024 bytes |
| Upload request timeout: | 60 seconds |
| Command request timeout: | 30 seconds |
| Retry count: | 3 |
| Gateway Priority: | Medium |
| E-mail addresses: | - |
| Verification interval: | 600 seconds |
| Maximum number of verification attempts: | 10 |
| Post-run Options |  |
| Auto restart upgrade: | 3 times |
| Auto complete upgrade: | Disabled |

- Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past meter firmware upgrades. If necessary, restart the FWU project.

- Monitor for any AP/Relay that failed the upgrade and send a list to the Communication Networks Quality Manager for investigation and triage.

- Collect all post upgrade data and record in the tracking spreadsheet.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- If all issues, if any, has been resolved, proceed to the next stage.

- Communicate results of Stage 2, and if proceeding to the next stage, to the relevant stakeholders.

### Stage 3 (All Access points and relays)

Resources Required: ACCG, UIQ Support or Data Analytics

In Stage 3, there is now high confidence that the new firmware does not pose any significant risk to the Aps/Relays functionality. All the remaining AP/Relay that needs to be upgraded to the new firmware will be covered in this stage.

Steps:

- Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

| Basic Information |  |
| --- | --- |
| Name: | Stage 3 - <Vendor> <AP/Relay Image Type> <Firmware> |
| Audit job: | - |
| Type: | <autofilled> |
| Version: | <autofilled> |
| Image: | Firware Image |
| Upgrade Settings |  |
| Seed density: | 3% of nodes are seeds |
| Upload image chunk size: | 1,024 bytes |
| Upload request timeout: | 60 seconds |
| Command request timeout: | 30 seconds |
| Retry count: | 3 |
| Gateway Priority: | Medium |
| E-mail addresses: | - |
| Verification interval: | 600 seconds |
| Maximum number of verification attempts: | 10 |
| Post-run Options |  |
| Auto restart upgrade: | 3 times |
| Auto complete upgrade: | Disabled |

- Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past meter firmware upgrades. If necessary, restart the FWU project.

- Monitor for any AP/Relays that failed the upgrade and send a list to the Communication Networks Quality Manager for investigation and triage.

- Collect all post upgrade data and record in the tracking spreadsheet.

- Compare the pre and post upgrade data in the tracking spreadsheet and verify the impact of the deployment of new firmware to the meter performance.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- If all issues, if any, has been resolved, proceed to the next stage.

- Communicate results of Stage 3, and if proceeding to the next stage, to the relevant stakeholders.

### BAU Stage (All remaining Access Points and relays)

Resources Required: ACCG, UIQ Support or Data Analytics

In the BAU stage, all the remaining meters shall be targeted and upgraded to the New firmware.

Steps:

- Create the FWU audit for each firmware image type. The suggested audit setting for each FWU audit shall be as follows:

| Basic Information |  |
| --- | --- |
| Name: | <Vendor> <Meter Type> <old Firmware> to <newFirmware> |
| Description: | Daily upgrade for <AP/Relay Type> from <old Firmware> to <new Firmware> |
| Firmware type: | <autofilled> |
| Image: | <autofilled> |
| Frequency: | Daily , Run time: 02:00 |
| Devices: | <see criteria below> |
| Upgrade devices: | Automatic |
| Upgrade Settings |  |
| Seed density: | 100% of nodes are seeds |
| Upload image chunk size: | 256 bytes |
| Upload request timeout: | 60 seconds |
| Command request timeout: | 30 seconds |
| Retry count: | 3 |
| Gateway Priority: | Medium |
| Verification interval: | 300 seconds |
| Maximum number of verification attempts: | 10 |
| E-mail addresses: | - |
| Post-run Options |  |
| Auto restart upgrade: | 3 times |
| Auto complete upgrade: | Enabled |
| Device Criteria: |  |
| NIC type: | <blank> |
| Device type: | AP/Relay |
| Meter type: | <autofilled> |
| D2G type: | <blank> |
| NIC architecture: | AKIO, ARM, RNI |
| meter.firmwareVersion | <old firmware> |

- Notify relevant stakeholders prior to commencement of the audit and automatic upgrade. UIQ Support team will need to monitor the backend system and UIQ application during the upgrade.

- Monitor the success rate and duration of each automatic firmware upgrade daily. Report any noticeable slowness in the upgrade compared to past Ap/Relay firmware upgrades. If necessary, restart the FWU project.

- Continue to monitor the events and look for any critical events, not limited to those listed below.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- Continue to monitor the upgrade success rate, critical events.

- Communicate firmware upgrade progress and any issues to relevant stakeholders.

# Deployment Roles and Responsibilities

## Deployment Lead

The deployment lead for the newnic firmware is Percy Arachchige.

## Go – No Go

Each stage will have a go-no go checkpoint with the following stakeholders as approvers:

| Deployment Stage | Role | Stakeholder |
| --- | --- | --- |
| Stage 1 Stage 2 | Metering Engineer • United Energy | Karl Ngo |
|  | Senior AMI Strategy Engineer • United Energy | Graeme Watson |
|  | AMI Communications Analyst • Network | Sangsukdee, Wayne |
|  | Communication Networks Laboratory Techni • Network | Njuguna, Kamau |
|  | AMI Communications Analyst • United Energy | Cherian, Jogy |
| Stage 3 BAU Upgrade | Metering Engineer • United Energy | Karl Ngo |
|  | Senior AMI Strategy Engineer • United Energy | Graeme Watson |
|  | AMI Communications Analyst • Network | Sangsukdee, Wayne |
|  | Communication Networks Laboratory Techni • Network | Njuguna, Kamau |
|  | AMI Communications Analyst • United Energy | Cherian, Jogy |

## Escalation

The first point of escalation will be the Communication Netwoworks Quality Manager and depending on the issue, he/she will contact the relevant stakeholders in the reviewer’s list.

## Stakeholder Communication

The stakeholders in the reviewer and approver list shall be notified of the progress and any issue found during the firmware upgrade deployment. The mode of communication shall be via email.

## Operational and Support Groups

- List the support to be provided for the deployment and post go live.  For example, what role is the service desk playing and have they been informed.  Will the Business team provide trained floor walkers on go live day?

- ACCG

  - Overall firmware upgrade process

  - Send progress report

- UIQ Support

  - General UIQ application support and monitoring

  - Support on data requests that can’t be easily retrieve from the UI

- Data Analytics

  - SIQ and PQ polling data monitoring

  - Support on data requests that can’t be easily retrieve from the UI

- AMI Data (MDP)

  - AMI data to market monitoring

Complete the table below, listing all required resources for the deployment.

# Identified Risks

| Ref | Description | Details | Mitigation |
| --- | --- | --- | --- |
| Risk#1 | Undesired AP/Relay functionality due to new meter firmware | AP/Relay stops functioning correctly resulting loss of functionality | - Critical tests have been done during testing. - Staged deployment of the NIC firmware. - Revert the firmware to the previous version |
| Risk#2 |  |  |  |

# Appendix

Include exports from ALM for the execution results and defects.

## FWU Progress Report

The following information shall be sent as part of the daily FWU progress report.

| Issue# | Summary | Status |
| --- | --- | --- |

| Project Name | Start | Stop | Total Devices | Succeeded | Failed | % completed |
| --- | --- | --- | --- | --- | --- | --- |

# Revision

| Version | Date | Updated by | Comments |
| --- | --- | --- | --- |
| 0.1 | 04 June 2024 | PA | Draft |
| 0.2 | 06 June 2024 | LJ | Added comments and minor edits |
| 0.3 | 18 June 2024 | PA | Recomanded comments added |