## Days
1 | Mon |  | Target Test Velocity per Tester | 8
2 | Tue |  | Total Planned # of test cases | 274
3 | Wed |  | Total Actual # of test cases | 361
4 | Thu |  | Allowance | 10%
5 | Fri |  | Effort (Man Days) | 37.675
6 | Sat |  | # of resources | 2
7 | Sun |  | # of days | 19
|  |  | Scheduled Start | 4555500%
Date | Day | Holiday | Scheduled Finish | 4558200%
4529200% | Mon | New Year's Day | Projected Finish | 4561220%
4531700% | Fri | Australia Day | Project Delay | 21
4536200% | Mon | Labour Day (VIC) | Project Delay | -10.53%
4538000% | Fri | Good Friday
4538100% | Sat | Easter Saturday | Original Deadline
4538200% | Sun | Easter Sunday | Adjusted Deadline (VPN)
4538300% | Mon | Easter Monday | New Deadline (Project)
4540700% | Thu | Anzac Day
4545300% | Mon | Kings's Birthday
4556200% | Fri | AFL Grand Final
4560100% | Tue | Melbourne Cup (VIC)
4565100% | Wed | Christmas | Target Test Velocity per Tester | 8
4565200% | Thu | Boxing Day | VPN - Planned # of test cases (UIQ-Patch123) | 0
4565300% | Fri | Powercor Day | VPN - Actual # of test cases (UIQ-Patch123) | #REF!
4565800% | Wed | New Year's Day
4568400% | Mon | Australia Day | Target Test Velocity per Tester | 8
4572600% | Mon | Labour Day (VIC) | UE - Planned # of test cases (Phase 2b) | 0
4576500% | Fri | Good Friday | UE - ACtual # of test cases (Phase 2b) | #REF!
4576600% | Sat | Easter Saturday
4576700% | Sun | Easter Sunday | Target Test Velocity per Tester | 8
4576800% | Mon | Easter Monday | UE - Planned # of test cases (Phase 2b) | 0
4577200% | Fri | Anzac Day | UE - ACtual # of test cases (Phase 2b) | #REF!
4581700% | Mon | Kings's Birthday
4592600% | Fri | AFL Grand Final
4596500% | Tue | Melbourne Cup (VIC)
4601600% | Thu | Christmas
4601700% | Fri | Boxing Day
4602000% | Mon | Powercor Day
Note on F10: Jarillas, Leonard: Need to manually looked at in the tracking tab

## 2024 - L&G R64 - Test Instances
Test Configuration: Test ID | Target Cycle: | Test Set: Name: | Test: Subject: | Test: Test Name: | Test: Test Priority: | Comments: | Exec Date: | Time | Test: Execution Status: | Status: | Tester: | Responsible Tester | Executed | Done | Name | Responsible Testers
36 | L&G 82-R64 | U3400 R6.4 - NIC5 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:17 | Blocked | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U3400 R6.4 - NIC5 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:17 | Blocked | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U3400 R6.4 - NIC3 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:16 | Blocked | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U3400 R6.4 - NIC3 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:16 | Blocked | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U1300 R6.4 - NIC5 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:15 | Blocked | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U1300 R6.4 - NIC5 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:15 | Blocked | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U1300 R6.4 - NIC3 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:14 | Blocked | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Meter state transitions - New to xxx to Active
36 | L&G 82-R64 | U1300 R6.4 - NIC3 | 001 - Commissioning | Meter state transitions - New to xxx to Active | 1-Critical |  | 4555900% | 17:14 | Blocked | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Meter state transitions - New to xxx to Active
32 | L&G 82-R64 | U1300 R6.4 - NIC3 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U1300 R6.4 - NIC3 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U1300 R6.4 - NIC5 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U1300 R6.4 - NIC5 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U3400 R6.4 - NIC3 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U3400 R6.4 - NIC3 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U3400 R6.4 - NIC5 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Reloading RMA meters into UIQ
32 | L&G 82-R64 | U3400 R6.4 - NIC5 | 001 - Commissioning | Reloading RMA meters into UIQ | 1-Critical |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Reloading RMA meters into UIQ
963 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 01 Meter Time synchronisation to NIC - forward within interval (Auto) | 2-High |  | 4556600% | 16:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 01 Meter Time synchronisation to NIC - forward within interval (Auto)
153 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 02 Meter Time synchronisation to NIC - forward within interval (Force) | 1-Critical |  | 4556700% | 11:26 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 02 Meter Time synchronisation to NIC - forward within interval (Force)
154 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 03 Meter Time synchronisation to NIC - backward within interval (Auto) | 2-High |  | 4556700% | 13:43 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 03 Meter Time synchronisation to NIC - backward within interval (Auto)
158 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 04 Meter Time synchronisation to NIC - backward within interval (Force) | 1-Critical |  | 4556700% | 14:37 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 04 Meter Time synchronisation to NIC - backward within interval (Force)
156 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 05 Meter Time synchronisation to NIC - forward crossing interval (Auto) | 2-High |  | 4556700% | 15:42 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 05 Meter Time synchronisation to NIC - forward crossing interval (Auto)
157 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 06 Meter Time synchronisation to NIC - forward crossing interval (Force) | 2-High |  | 4556800% | 11:04 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 06 Meter Time synchronisation to NIC - forward crossing interval (Force)
159 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 07 Meter Time synchronisation to NIC - backward crossing interval (Auto) | 2-High |  | 4557900% | 16:18 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 07 Meter Time synchronisation to NIC - backward crossing interval (Auto)
964 | L&G 82-R64 | U3400 R6.4 - NIC3 | 004 - Time | 08 Meter Time synchronisation to NIC - backward crossing interval (Force) | 2-High |  | 4557900% | 16:20 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - 08 Meter Time synchronisation to NIC - backward crossing interval (Force)
963 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 01 Meter Time synchronisation to NIC - forward within interval (Auto) | 2-High |  | 4557600% | 10:19 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 01 Meter Time synchronisation to NIC - forward within interval (Auto)
153 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 02 Meter Time synchronisation to NIC - forward within interval (Force) | 1-Critical |  | 4557600% | 11:41 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 02 Meter Time synchronisation to NIC - forward within interval (Force)
154 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 03 Meter Time synchronisation to NIC - backward within interval (Auto) | 2-High |  | 4557600% | 14:52 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 03 Meter Time synchronisation to NIC - backward within interval (Auto)
158 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 04 Meter Time synchronisation to NIC - backward within interval (Force) | 1-Critical |  | 4557600% | 15:49 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 04 Meter Time synchronisation to NIC - backward within interval (Force)
156 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 05 Meter Time synchronisation to NIC - forward crossing interval (Auto) | 2-High |  | 4557600% | 17:15 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 05 Meter Time synchronisation to NIC - forward crossing interval (Auto)
157 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 06 Meter Time synchronisation to NIC - forward crossing interval (Force) | 2-High |  | 4557900% | 9:58 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 06 Meter Time synchronisation to NIC - forward crossing interval (Force)
159 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 07 Meter Time synchronisation to NIC - backward crossing interval (Auto) | 2-High |  | 4557900% | 11:20 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 07 Meter Time synchronisation to NIC - backward crossing interval (Auto)
964 | L&G 82-R64 | U1300 R6.4 - NIC3 | 004 - Time | 08 Meter Time synchronisation to NIC - backward crossing interval (Force) | 2-High |  | 4557900% | 13:12 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - 08 Meter Time synchronisation to NIC - backward crossing interval (Force)
963 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 01 Meter Time synchronisation to NIC - forward within interval (Auto) | 2-High |  | 4556600% | 16:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 01 Meter Time synchronisation to NIC - forward within interval (Auto)
153 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 02 Meter Time synchronisation to NIC - forward within interval (Force) | 1-Critical |  | 4556700% | 11:26 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 02 Meter Time synchronisation to NIC - forward within interval (Force)
154 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 03 Meter Time synchronisation to NIC - backward within interval (Auto) | 2-High |  | 4556700% | 13:43 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 03 Meter Time synchronisation to NIC - backward within interval (Auto)
158 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 04 Meter Time synchronisation to NIC - backward within interval (Force) | 1-Critical |  | 4556700% | 14:37 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 04 Meter Time synchronisation to NIC - backward within interval (Force)
156 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 05 Meter Time synchronisation to NIC - forward crossing interval (Auto) | 2-High |  | 4556700% | 15:38 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 05 Meter Time synchronisation to NIC - forward crossing interval (Auto)
157 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 06 Meter Time synchronisation to NIC - forward crossing interval (Force) | 2-High |  | 4556800% | 11:04 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 06 Meter Time synchronisation to NIC - forward crossing interval (Force)
159 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 07 Meter Time synchronisation to NIC - backward crossing interval (Auto) | 2-High |  | 4557900% | 16:21 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 07 Meter Time synchronisation to NIC - backward crossing interval (Auto)
964 | L&G 82-R64 | U3400 R6.4 - NIC5 | 004 - Time | 08 Meter Time synchronisation to NIC - backward crossing interval (Force) | 2-High |  | 4557900% | 16:22 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - 08 Meter Time synchronisation to NIC - backward crossing interval (Force)
963 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 01 Meter Time synchronisation to NIC - forward within interval (Auto) | 2-High |  | 4557600% | 10:23 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 01 Meter Time synchronisation to NIC - forward within interval (Auto)
153 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 02 Meter Time synchronisation to NIC - forward within interval (Force) | 1-Critical |  | 4557600% | 11:52 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 02 Meter Time synchronisation to NIC - forward within interval (Force)
154 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 03 Meter Time synchronisation to NIC - backward within interval (Auto) | 2-High |  | 4557600% | 14:43 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 03 Meter Time synchronisation to NIC - backward within interval (Auto)
158 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 04 Meter Time synchronisation to NIC - backward within interval (Force) | 1-Critical |  | 4557600% | 15:52 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 04 Meter Time synchronisation to NIC - backward within interval (Force)
156 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 05 Meter Time synchronisation to NIC - forward crossing interval (Auto) | 2-High |  | 4557600% | 17:19 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 05 Meter Time synchronisation to NIC - forward crossing interval (Auto)
157 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 06 Meter Time synchronisation to NIC - forward crossing interval (Force) | 2-High |  | 4557900% | 9:59 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 06 Meter Time synchronisation to NIC - forward crossing interval (Force)
159 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 07 Meter Time synchronisation to NIC - backward crossing interval (Auto) | 2-High |  | 4557900% | 11:33 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 07 Meter Time synchronisation to NIC - backward crossing interval (Auto)
964 | L&G 82-R64 | U1300 R6.4 - NIC5 | 004 - Time | 08 Meter Time synchronisation to NIC - backward crossing interval (Force) | 2-High |  | 4557900% | 13:15 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - 08 Meter Time synchronisation to NIC - backward crossing interval (Force)
39 | L&G 82-R64 | U3400 R6.4 - NIC3 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted | 1-Critical |  | 4557300% | 10:11 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted
1703 | L&G 82-R64 | U3400 R6.4 - NIC3 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted | 1-Critical | This Test is performed on U1300 meter | 4557900% | 16:29 | Failed | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted
38 | L&G 82-R64 | U3400 R6.4 - NIC3 | 007 - Meter Firmware | Meter firmware audit | 1-Critical |  | 4556900% | 9:11 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter firmware audit
39 | L&G 82-R64 | U1300 R6.4 - NIC3 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted | 1-Critical |  | 4555500% | 11:00 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted
1703 | L&G 82-R64 | U1300 R6.4 - NIC3 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted | 1-Critical |  | 4558100% | 9:32 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted
38 | L&G 82-R64 | U1300 R6.4 - NIC3 | 007 - Meter Firmware | Meter firmware audit | 1-Critical |  | 4555500% | 13:20 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter firmware audit
39 | L&G 82-R64 | U3400 R6.4 - NIC5 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted | 1-Critical |  | 4557300% | 10:12 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted
1703 | L&G 82-R64 | U3400 R6.4 - NIC5 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted | 1-Critical | This Test is performed on U1300 meter | 4558000% | 10:46 | Failed | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted
38 | L&G 82-R64 | U3400 R6.4 - NIC5 | 007 - Meter Firmware | Meter firmware audit | 1-Critical |  | 4556900% | 9:11 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter firmware audit
39 | L&G 82-R64 | U1300 R6.4 - NIC5 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted | 1-Critical |  | 4555500% | 11:21 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted
1703 | L&G 82-R64 | U1300 R6.4 - NIC5 | 007 - Meter Firmware | FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted | 1-Critical | NIC320 meter has been tested | 4558000% | 11:52 | Failed | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted
38 | L&G 82-R64 | U1300 R6.4 - NIC5 | 007 - Meter Firmware | Meter firmware audit | 1-Critical |  | 4555500% | 15:01 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter firmware audit
41 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008 - Meter Program | Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ) | 1-Critical |  | 4557200% | 15:37 | Not Completed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ)
42 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008 - Meter Program | Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ) | 1-Critical |  | 4557300% | 17:49 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ)
61 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008 - Meter Program | Meter Program - export events | 1-Critical |  | 4556500% | 13:46 | RBT | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Program - export events
40 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008 - Meter Program | Meter program audit | 1-Critical |  | 4557200% | 16:00 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter program audit
41 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008 - Meter Program | Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ) | 1-Critical |  | 4556800% | 14:49 | Not Completed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ)
42 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008 - Meter Program | Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ) | 1-Critical |  | 4556800% | 15:59 | Passed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ)
61 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008 - Meter Program | Meter Program - export events | 1-Critical | Covered in Meter Data Integrity test | 4558900% | 14:44 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Meter Program - export events
40 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008 - Meter Program | Meter program audit | 1-Critical |  | 4556600% | 16:38 | Passed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter program audit
41 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008 - Meter Program | Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ) | 1-Critical |  | 4557200% | 15:07 | Not Completed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ)
42 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008 - Meter Program | Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ) | 1-Critical |  | 4557300% | 17:49 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ)
61 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008 - Meter Program | Meter Program - export events | 1-Critical |  | 4556500% | 13:34 | RBT | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Program - export events
40 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008 - Meter Program | Meter program audit | 1-Critical |  | 4557200% | 16:00 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter program audit
41 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008 - Meter Program | Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ) | 1-Critical |  | 4556800% | 14:41 | Not Completed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ)
42 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008 - Meter Program | Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ) | 1-Critical |  | 4556800% | 16:32 | Passed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ)
61 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008 - Meter Program | Meter Program - export events | 1-Critical | Covered in Meter Data Integrity test | 4558900% | 14:46 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Meter Program - export events
40 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008 - Meter Program | Meter program audit | 1-Critical |  | 4556600% | 16:44 | Passed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter program audit
141 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008 - Meter Program | Meter Program - NIC program seal | 1-Critical |  | 4556500% | 10:32 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Program - NIC program seal
141 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008 - Meter Program | Meter Program - NIC program seal | 1-Critical |  | 4557400% | 15:55 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Program - NIC program seal
141 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008 - Meter Program | Meter Program - NIC program seal | 1-Critical |  | 4557400% | 16:00 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Program - NIC program seal
141 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008 - Meter Program | Meter Program - NIC program seal | 1-Critical |  | 4556500% | 10:32 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Program - NIC program seal
140 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008 - Meter Program | Meter Program - Partial programming (Remote) | 1-Critical |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Meter Program - Partial programming (Remote)
140 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008 - Meter Program | Meter Program - Partial programming (Remote) | 1-Critical |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Meter Program - Partial programming (Remote)
140 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008 - Meter Program | Meter Program - Partial programming (Remote) | 1-Critical |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Meter Program - Partial programming (Remote)
140 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008 - Meter Program | Meter Program - Partial programming (Remote) | 1-Critical |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Meter Program - Partial programming (Remote)
1770 | L&G 82-R64 | U1300 R6.4 - NIC3 | 008A - Meter Program Tests | L&G_LP_Enable | 3-Medium |  | 4557500% | 16:00 | Not Completed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - L&G_LP_Enable
1770 | L&G 82-R64 | U1300 R6.4 - NIC5 | 008A - Meter Program Tests | L&G_LP_Enable | 3-Medium |  | 4557500% | 16:01 | Not Completed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - L&G_LP_Enable
1770 | L&G 82-R64 | U3400 R6.4 - NIC3 | 008A - Meter Program Tests | L&G_LP_Enable | 3-Medium |  | 4557900% | 16:17 | Not Completed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - L&G_LP_Enable
1770 | L&G 82-R64 | U3400 R6.4 - NIC5 | 008A - Meter Program Tests | L&G_LP_Enable | 3-Medium |  | 4556100% | 14:17 | Not Completed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - L&G_LP_Enable
111 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | Meter Accuracy | 1-Critical | Report from L&G is used for this test. | 4558900% | 13:40 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Meter Accuracy
1709 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Full) | 1-Critical |  | 4557600% | 14:50 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Data Integrity - Meter to UIQ (Full)
66 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - C1219 Read | 1-Critical |  | 4556000% | 14:03 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - AMM - On Demand Read - C1219 Read
63 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - Interval | 1-Critical |  | 4556000% | 14:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - AMM - On Demand Read - Interval
62 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - New Data | 1-Critical |  | 4556000% | 15:53 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - AMM - On Demand Read - New Data
64 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - Register | 1-Critical |  | 4556000% | 17:09 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - AMM - On Demand Read - Register
65 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - Stored Self Read | 1-Critical |  | 4556100% | 10:33 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - AMM - On Demand Read - Stored Self Read
59 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - AMM export | 1-Critical |  | 4557900% | 12:53 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Data Integrity - AMM export
58 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - EBQK | 1-Critical | MOG group will be doing this test for R64 | 4558000% | 11:03 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Meter Data Integrity - EBQK
111 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | Meter Accuracy | 1-Critical |  | 4558900% | 14:38 | RBT | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Accuracy
1709 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Full) | 1-Critical |  | 4556600% | 13:52 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Data Integrity - Meter to UIQ (Full)
66 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - C1219 Read | 1-Critical |  | 4555900% | 8:38 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - AMM - On Demand Read - C1219 Read
63 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - Interval | 1-Critical |  | 4555900% | 8:42 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - AMM - On Demand Read - Interval
62 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - New Data | 1-Critical |  | 4555900% | 9:15 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - AMM - On Demand Read - New Data
64 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - Register | 1-Critical |  | 4555900% | 9:22 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - AMM - On Demand Read - Register
65 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - Stored Self Read | 1-Critical |  | 4555900% | 10:16 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - AMM - On Demand Read - Stored Self Read
59 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - AMM export | 1-Critical |  | 4557200% | 10:39 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Data Integrity - AMM export
58 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - EBQK | 1-Critical | To be covered under meter accuracy test | 4558000% | 11:55 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Meter Data Integrity - EBQK
111 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | Meter Accuracy | 1-Critical | Report from L&G is used for this test. | 4558900% | 13:36 | RBT | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Accuracy
1709 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Full) | 1-Critical |  | 4557600% | 15:03 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Data Integrity - Meter to UIQ (Full)
66 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - C1219 Read | 1-Critical |  | 4556000% | 14:03 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - AMM - On Demand Read - C1219 Read
63 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - Interval | 1-Critical |  | 4556000% | 14:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - AMM - On Demand Read - Interval
62 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - New Data | 1-Critical |  | 4556000% | 15:53 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - AMM - On Demand Read - New Data
64 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - Register | 1-Critical |  | 4556000% | 17:07 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - AMM - On Demand Read - Register
65 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - Stored Self Read | 1-Critical |  | 4556100% | 10:34 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - AMM - On Demand Read - Stored Self Read
59 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - AMM export | 1-Critical |  | 4557900% | 12:34 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Data Integrity - AMM export
58 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - EBQK | 1-Critical | MOG group will be doing this test for R64 | 4558900% | 13:57 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Meter Data Integrity - EBQK
111 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | Meter Accuracy | 1-Critical |  | 4558900% | 14:27 | RBT | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Accuracy
1709 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Full) | 1-Critical |  | 4558000% | 15:21 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Data Integrity - Meter to UIQ (Full)
66 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - C1219 Read | 1-Critical |  | 4556500% | 13:39 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - AMM - On Demand Read - C1219 Read
63 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - Interval | 1-Critical |  | 4556500% | 13:45 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - AMM - On Demand Read - Interval
62 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - New Data | 1-Critical |  | 4556500% | 14:28 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - AMM - On Demand Read - New Data
64 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - Register | 1-Critical |  | 4556500% | 14:30 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - AMM - On Demand Read - Register
65 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - Stored Self Read | 1-Critical |  | 4556500% | 14:34 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - AMM - On Demand Read - Stored Self Read
59 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - AMM export | 1-Critical |  | 4557200% | 11:15 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Data Integrity - AMM export
58 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - EBQK | 1-Critical | Test to be covered under meter accuracy test | 4558000% | 11:53 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Meter Data Integrity - EBQK
1710 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Sanity) | 1-Critical |  | 4557500% | 10:08 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter Data Integrity - Meter to UIQ (Sanity)
1710 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Sanity) | 1-Critical |  | 4557500% | 11:31 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter Data Integrity - Meter to UIQ (Sanity)
1710 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Sanity) | 1-Critical |  | 4557600% | 12:09 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter Data Integrity - Meter to UIQ (Sanity)
1710 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | Meter Data Integrity - Meter to UIQ (Sanity) | 1-Critical |  | 4557600% | 12:09 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter Data Integrity - Meter to UIQ (Sanity)
33 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - NIC Event Log | 1-Critical |  | 4557400% | 16:11 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - AMM - On Demand Read - NIC Event Log
33 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - NIC Event Log | 1-Critical |  | 4557400% | 16:12 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - AMM - On Demand Read - NIC Event Log
33 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | AMM - On Demand Read - NIC Event Log | 1-Critical |  | 4556100% | 11:03 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - AMM - On Demand Read - NIC Event Log
33 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | AMM - On Demand Read - NIC Event Log | 1-Critical |  | 4556100% | 11:04 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - AMM - On Demand Read - NIC Event Log
60 | L&G 82-R64 | U1300 R6.4 - NIC3 | 009 - Metrology | Meter display - register resolution | 3-Medium |  | 4557200% | 16:33 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter display - register resolution
60 | L&G 82-R64 | U1300 R6.4 - NIC5 | 009 - Metrology | Meter display - register resolution | 3-Medium |  | 4557200% | 16:34 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter display - register resolution
60 | L&G 82-R64 | U3400 R6.4 - NIC3 | 009 - Metrology | Meter display - register resolution | 3-Medium |  | 4557200% | 12:16 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter display - register resolution
60 | L&G 82-R64 | U3400 R6.4 - NIC5 | 009 - Metrology | Meter display - register resolution | 3-Medium |  | 4557200% | 12:16 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter display - register resolution
144 | L&G 82-R64 | U3400 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor - Arm Remotely | 3-Medium |  | 4557200% | 16:04 | N/A | N/A | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | N/A | U3400 R6.4 - NIC3 - Meter supply contactor - Arm Remotely
69 | L&G 82-R64 | U3400 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor - Remote Lockout | 1-Critical |  | 4556500% | 16:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter supply contactor - Remote Lockout
68 | L&G 82-R64 | U3400 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor connect disconnect - local | 1-Critical |  | 4556500% | 17:13 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter supply contactor connect disconnect - local
67 | L&G 82-R64 | U3400 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor connect disconnect - remote | 1-Critical |  | 4556500% | 17:29 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter supply contactor connect disconnect - remote
144 | L&G 82-R64 | U1300 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor - Arm Remotely | 3-Medium |  | 4557500% | 8:41 | N/A | N/A | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | No Run | N/A | U1300 R6.4 - NIC3 - Meter supply contactor - Arm Remotely
69 | L&G 82-R64 | U1300 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor - Remote Lockout | 1-Critical |  | 4557200% | 13:30 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter supply contactor - Remote Lockout
68 | L&G 82-R64 | U1300 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor connect disconnect - local | 1-Critical |  | 4556800% | 16:40 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter supply contactor connect disconnect - local
67 | L&G 82-R64 | U1300 R6.4 - NIC3 | 010 - Supply Contactor | Meter supply contactor connect disconnect - remote | 1-Critical |  | 4556800% | 15:19 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter supply contactor connect disconnect - remote
144 | L&G 82-R64 | U3400 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor - Arm Remotely | 3-Medium |  | 4557200% | 16:05 | N/A | N/A | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | N/A | U3400 R6.4 - NIC5 - Meter supply contactor - Arm Remotely
69 | L&G 82-R64 | U3400 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor - Remote Lockout | 1-Critical |  | 4556500% | 16:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter supply contactor - Remote Lockout
68 | L&G 82-R64 | U3400 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor connect disconnect - local | 1-Critical |  | 4556500% | 17:12 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter supply contactor connect disconnect - local
67 | L&G 82-R64 | U3400 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor connect disconnect - remote | 1-Critical |  | 4556500% | 17:29 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter supply contactor connect disconnect - remote
144 | L&G 82-R64 | U1300 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor - Arm Remotely | 3-Medium | Not applicable to L&G meters | 4558000% | 11:54 | N/A | N/A | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | No Run | N/A | U1300 R6.4 - NIC5 - Meter supply contactor - Arm Remotely
69 | L&G 82-R64 | U1300 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor - Remote Lockout | 1-Critical |  | 4557200% | 15:09 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter supply contactor - Remote Lockout
68 | L&G 82-R64 | U1300 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor connect disconnect - local | 1-Critical |  | 4556800% | 16:43 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter supply contactor connect disconnect - local
67 | L&G 82-R64 | U1300 R6.4 - NIC5 | 010 - Supply Contactor | Meter supply contactor connect disconnect - remote | 1-Critical |  | 4556800% | 15:24 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter supply contactor connect disconnect - remote
71 | L&G 82-R64 | U3400 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Disabled | 1-Critical |  | 4556600% | 10:07 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Auto-Disconnect - Disabled
70 | L&G 82-R64 | U3400 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Enabled | 1-Critical |  | 4556600% | 12:13 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Auto-Disconnect - Enabled
185 | L&G 82-R64 | U3400 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Override For NAP (L+G) | 2-High |  | 4556600% | 12:58 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Auto-Disconnect - Override For NAP (L+G)
89 | L&G 82-R64 | U3400 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Remote Lockout | 4-Low |  | 4556600% | 13:22 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Auto-Disconnect - Remote Lockout
71 | L&G 82-R64 | U1300 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Disabled | 1-Critical |  | 4556900% | 9:37 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Auto-Disconnect - Disabled
70 | L&G 82-R64 | U1300 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Enabled | 1-Critical |  | 4556900% | 8:57 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Auto-Disconnect - Enabled
185 | L&G 82-R64 | U1300 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Override For NAP (L+G) | 2-High |  | 4556900% | 10:50 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Auto-Disconnect - Override For NAP (L+G)
89 | L&G 82-R64 | U1300 R6.4 - NIC3 | 011 - Auto-Disconnection | Auto-Disconnect - Remote Lockout | 4-Low |  | 4556900% | 11:04 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Auto-Disconnect - Remote Lockout
71 | L&G 82-R64 | U3400 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Disabled | 1-Critical |  | 4556600% | 10:07 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Auto-Disconnect - Disabled
70 | L&G 82-R64 | U3400 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Enabled | 1-Critical |  | 4556600% | 12:59 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Auto-Disconnect - Enabled
185 | L&G 82-R64 | U3400 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Override For NAP (L+G) | 2-High |  | 4556600% | 12:58 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Auto-Disconnect - Override For NAP (L+G)
89 | L&G 82-R64 | U3400 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Remote Lockout | 4-Low |  | 4556600% | 13:22 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Auto-Disconnect - Remote Lockout
71 | L&G 82-R64 | U1300 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Disabled | 1-Critical |  | 4556900% | 9:44 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Auto-Disconnect - Disabled
70 | L&G 82-R64 | U1300 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Enabled | 1-Critical |  | 4556900% | 8:58 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Auto-Disconnect - Enabled
185 | L&G 82-R64 | U1300 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Override For NAP (L+G) | 2-High |  | 4556900% | 10:50 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Auto-Disconnect - Override For NAP (L+G)
89 | L&G 82-R64 | U1300 R6.4 - NIC5 | 011 - Auto-Disconnection | Auto-Disconnect - Remote Lockout | 4-Low |  | 4556900% | 11:10 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Auto-Disconnect - Remote Lockout
74 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Meter load contactor - remote override (close) | 1-Critical |  | 4555500% | 9:55 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter load contactor - remote override (close)
73 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Meter load contactor - remote override (open) | 1-Critical |  | 4555500% | 11:03 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter load contactor - remote override (open)
75 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Meter load contactor - switching schedule 5-on-5-off | 1-Critical |  | 4557200% | 10:23 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter load contactor - switching schedule 5-on-5-off
122 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Boost Primacy - Boost time longer than LC override | 2-High |  | 4556800% | 16:18 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Boost Primacy - Boost time longer than LC override
123 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Boost Primacy - Disabled | 2-High |  | 4555500% | 13:20 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Boost Primacy - Disabled
1725 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Boost Primacy - Enable-Disable | 2-High |  | 4555500% | 15:00 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Boost Primacy - Enable-Disable
90 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Boost operation - Disabled | 2-High |  | 4555900% | 9:38 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Boost operation - Disabled
76 | L&G 82-R64 | U3400 R6.4 - NIC3 | 012 - Load Contactor | Boost operation - Enabled - Boost (Boost Duration) minutes | 1-Critical |  | 4555900% | 12:37 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Boost operation - Enabled - Boost (Boost Duration) minutes
74 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Meter load contactor - remote override (close) | 1-Critical |  | 4555500% | 14:11 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter load contactor - remote override (close)
73 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Meter load contactor - remote override (open) | 1-Critical |  | 4555500% | 14:51 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter load contactor - remote override (open)
75 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Meter load contactor - switching schedule 5-on-5-off | 1-Critical |  | 4555800% | 9:04 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter load contactor - switching schedule 5-on-5-off
122 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Boost Primacy - Boost time longer than LC override | 2-High |  | 4556900% | 14:38 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Boost Primacy - Boost time longer than LC override
123 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Boost Primacy - Disabled | 2-High |  | 4556900% | 16:04 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Boost Primacy - Disabled
1725 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Boost Primacy - Enable-Disable | 2-High |  | 4556900% | 16:44 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Boost Primacy - Enable-Disable
90 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Boost operation - Disabled | 2-High |  | 4557200% | 16:23 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Boost operation - Disabled
76 | L&G 82-R64 | U1300 R6.4 - NIC3 | 012 - Load Contactor | Boost operation - Enabled - Boost (Boost Duration) minutes | 1-Critical |  | 4557300% | 11:24 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Boost operation - Enabled - Boost (Boost Duration) minutes
74 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Meter load contactor - remote override (close) | 1-Critical |  | 4555500% | 9:55 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter load contactor - remote override (close)
73 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Meter load contactor - remote override (open) | 1-Critical |  | 4555500% | 11:00 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter load contactor - remote override (open)
75 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Meter load contactor - switching schedule 5-on-5-off | 1-Critical |  | 4557200% | 10:23 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter load contactor - switching schedule 5-on-5-off
122 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Boost Primacy - Boost time longer than LC override | 2-High |  | 4556800% | 16:19 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Boost Primacy - Boost time longer than LC override
123 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Boost Primacy - Disabled | 2-High |  | 4555500% | 13:20 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Boost Primacy - Disabled
1725 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Boost Primacy - Enable-Disable | 2-High |  | 4555500% | 15:01 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Boost Primacy - Enable-Disable
90 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Boost operation - Disabled | 2-High |  | 4555900% | 9:38 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Boost operation - Disabled
76 | L&G 82-R64 | U3400 R6.4 - NIC5 | 012 - Load Contactor | Boost operation - Enabled - Boost (Boost Duration) minutes | 1-Critical |  | 4555900% | 12:37 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Boost operation - Enabled - Boost (Boost Duration) minutes
74 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Meter load contactor - remote override (close) | 1-Critical |  | 4555500% | 14:12 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter load contactor - remote override (close)
73 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Meter load contactor - remote override (open) | 1-Critical |  | 4555500% | 14:57 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter load contactor - remote override (open)
75 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Meter load contactor - switching schedule 5-on-5-off | 1-Critical |  | 4555800% | 9:24 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter load contactor - switching schedule 5-on-5-off
122 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Boost Primacy - Boost time longer than LC override | 2-High |  | 4556900% | 14:40 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Boost Primacy - Boost time longer than LC override
123 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Boost Primacy - Disabled | 2-High |  | 4556900% | 16:12 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Boost Primacy - Disabled
1725 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Boost Primacy - Enable-Disable | 2-High |  | 4556900% | 16:57 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Boost Primacy - Enable-Disable
90 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Boost operation - Disabled | 2-High |  | 4557200% | 16:24 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Boost operation - Disabled
76 | L&G 82-R64 | U1300 R6.4 - NIC5 | 012 - Load Contactor | Boost operation - Enabled - Boost (Boost Duration) minutes | 1-Critical |  | 4557300% | 11:29 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Boost operation - Enabled - Boost (Boost Duration) minutes
79 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | Loss of phase supply on 3-phase meters | 1-Critical |  | 4557400% | 12:43 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Loss of phase supply on 3-phase meters
78 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | Loss of supply - threshold | 1-Critical |  | 4557400% | 16:49 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Loss of supply - threshold
120 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | Over temperature event - L&G meters | 2-High |  | 4558000% | 10:52 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Over temperature event - L&G meters
146 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | QoS - Low PF detection | 1-Critical |  | 4557600% | 15:05 | N/A | N/A | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | N/A | U3400 R6.4 - NIC3 - QoS - Low PF detection
80 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | QoS - Overvoltage and Undervoltage | 1-Critical |  | 4557400% | 10:56 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - QoS - Overvoltage and Undervoltage
145 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | QoS - Voltage failure detection | 1-Critical |  | 4557400% | 11:05 | N/A | N/A | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | N/A | U3400 R6.4 - NIC3 - QoS - Voltage failure detection
78 | L&G 82-R64 | U1300 R6.4 - NIC3 | 014 - QoS | Loss of supply - threshold | 1-Critical |  | 4557300% | 14:35 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Loss of supply - threshold
120 | L&G 82-R64 | U1300 R6.4 - NIC3 | 014 - QoS | Over temperature event - L&G meters | 2-High |  | 4558000% | 11:56 | RBT | Not Completed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Unfinished | U1300 R6.4 - NIC3 - Over temperature event - L&G meters
146 | L&G 82-R64 | U1300 R6.4 - NIC3 | 014 - QoS | QoS - Low PF detection | 1-Critical | Not applicable to L&G meters | 4557400% | 9:03 | N/A | N/A | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | No Run | N/A | U1300 R6.4 - NIC3 - QoS - Low PF detection
80 | L&G 82-R64 | U1300 R6.4 - NIC3 | 014 - QoS | QoS - Overvoltage and Undervoltage | 1-Critical |  | 4557200% | 15:59 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - QoS - Overvoltage and Undervoltage
145 | L&G 82-R64 | U1300 R6.4 - NIC3 | 014 - QoS | QoS - Voltage failure detection | 1-Critical | Not applicable to L&G meters | 4557400% | 9:09 | N/A | N/A | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | No Run | N/A | U1300 R6.4 - NIC3 - QoS - Voltage failure detection
79 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | Loss of phase supply on 3-phase meters | 1-Critical |  | 4557400% | 12:43 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Loss of phase supply on 3-phase meters
78 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | Loss of supply - threshold | 1-Critical |  | 4557400% | 16:49 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Loss of supply - threshold
120 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | Over temperature event - L&G meters | 2-High | This Test is performed on U1300 Meters | 4558000% | 10:50 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Over temperature event - L&G meters
146 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | QoS - Low PF detection | 1-Critical |  | 4557600% | 15:05 | N/A | N/A | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | N/A | U3400 R6.4 - NIC5 - QoS - Low PF detection
80 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | QoS - Overvoltage and Undervoltage | 1-Critical |  | 4557400% | 10:56 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - QoS - Overvoltage and Undervoltage
145 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | QoS - Voltage failure detection | 1-Critical |  | 4557400% | 11:05 | N/A | N/A | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | N/A | U3400 R6.4 - NIC5 - QoS - Voltage failure detection
78 | L&G 82-R64 | U1300 R6.4 - NIC5 | 014 - QoS | Loss of supply - threshold | 1-Critical |  | 4557300% | 14:42 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Loss of supply - threshold
120 | L&G 82-R64 | U1300 R6.4 - NIC5 | 014 - QoS | Over temperature event - L&G meters | 2-High | NIC320 meter has been tested | 4558000% | 11:53 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Over temperature event - L&G meters
146 | L&G 82-R64 | U1300 R6.4 - NIC5 | 014 - QoS | QoS - Low PF detection | 1-Critical | Not applicable to L&G meters | 4557400% | 9:04 | N/A | N/A | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | No Run | N/A | U1300 R6.4 - NIC5 - QoS - Low PF detection
80 | L&G 82-R64 | U1300 R6.4 - NIC5 | 014 - QoS | QoS - Overvoltage and Undervoltage | 1-Critical |  | 4557200% | 16:01 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - QoS - Overvoltage and Undervoltage
145 | L&G 82-R64 | U1300 R6.4 - NIC5 | 014 - QoS | QoS - Voltage failure detection | 1-Critical | Not applicable to L&G meters | 4557400% | 9:12 | N/A | N/A | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | No Run | N/A | U1300 R6.4 - NIC5 - QoS - Voltage failure detection
77 | L&G 82-R64 | U1300 R6.4 - NIC3 | 014 - QoS | Loss of supply - Verify last gasp for multiple meter outage | 1-Critical |  | 4557400% | 16:35 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Loss of supply - Verify last gasp for multiple meter outage
77 | L&G 82-R64 | U1300 R6.4 - NIC5 | 014 - QoS | Loss of supply - Verify last gasp for multiple meter outage | 1-Critical |  | 4557400% | 16:25 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Loss of supply - Verify last gasp for multiple meter outage
77 | L&G 82-R64 | U3400 R6.4 - NIC3 | 014 - QoS | Loss of supply - Verify last gasp for multiple meter outage | 1-Critical |  | 4557500% | 10:15 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Loss of supply - Verify last gasp for multiple meter outage
77 | L&G 82-R64 | U3400 R6.4 - NIC5 | 014 - QoS | Loss of supply - Verify last gasp for multiple meter outage | 1-Critical |  | 4557400% | 17:28 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Loss of supply - Verify last gasp for multiple meter outage
148 | L&G 82-R64 | U3400 R6.4 - NIC3 | 015 - SIQ | SIQ Profile Sanity Check | 1-Critical |  | 4557500% | 17:19 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - SIQ Profile Sanity Check
148 | L&G 82-R64 | U1300 R6.4 - NIC3 | 015 - SIQ | SIQ Profile Sanity Check | 1-Critical |  | 4557400% | 12:53 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - SIQ Profile Sanity Check
148 | L&G 82-R64 | U3400 R6.4 - NIC5 | 015 - SIQ | SIQ Profile Sanity Check | 1-Critical |  | 4557500% | 17:19 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - SIQ Profile Sanity Check
148 | L&G 82-R64 | U1300 R6.4 - NIC5 | 015 - SIQ | SIQ Profile Sanity Check | 1-Critical |  | 4557400% | 13:15 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - SIQ Profile Sanity Check
106 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Display meter consumption on IHD | 1-Critical |  | 4557900% | 15:43 | RBT | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - HCM - Display meter consumption on IHD
106 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Display meter consumption on IHD | 1-Critical |  | 4557900% | 15:06 | RBT | Blocked | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | Blocked | U3400 R6.4 - NIC3 - HCM - Display meter consumption on IHD
106 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Display meter consumption on IHD | 1-Critical | No appropriate meter with HAN certificate but passed on NIC320 meter | 4558000% | 14:33 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Display meter consumption on IHD
106 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Display meter consumption on IHD | 1-Critical |  | 4557900% | 15:16 | RBT | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - HCM - Display meter consumption on IHD
104 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Support for 2E meters metering cluster | 3-Medium |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Support for 2E meters metering cluster
104 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Support for 2E meters metering cluster | 3-Medium |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Support for 2E meters metering cluster
104 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Support for 2E meters metering cluster | 3-Medium |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Support for 2E meters metering cluster
104 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Support for 2E meters metering cluster | 3-Medium |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Support for 2E meters metering cluster
93 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Import IHD | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Import IHD
94 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Import ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Import ESI
95 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Sync ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Sync ESI
96 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Provision ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Provision ESI
97 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Associate IHD to ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Associate IHD to ESI
98 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Join IHD to ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Join IHD to ESI
99 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Ping IHD via ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Ping IHD via ESI
101 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Unjoin IHD to ESI | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Unjoin IHD to ESI
102 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - HAN secure key establishment | 3-Medium |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - HAN secure key establishment
103 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | HCM - Enroll ESI to HCM program | 3-Medium |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - HCM - Enroll ESI to HCM program
105 | L&G 82-R64 | U1300 R6.4 - NIC3 | 016 - HAN | NC - HAN radio diagnostic commands | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - NC - HAN radio diagnostic commands
93 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Import IHD | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Import IHD
94 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Import ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Import ESI
95 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Sync ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Sync ESI
96 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Provision ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Provision ESI
97 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Associate IHD to ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Associate IHD to ESI
98 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Join IHD to ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Join IHD to ESI
99 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Ping IHD via ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Ping IHD via ESI
101 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Unjoin IHD to ESI | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Unjoin IHD to ESI
102 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - HAN secure key establishment | 3-Medium |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - HAN secure key establishment
103 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | HCM - Enroll ESI to HCM program | 3-Medium |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Enroll ESI to HCM program
105 | L&G 82-R64 | U1300 R6.4 - NIC5 | 016 - HAN | NC - HAN radio diagnostic commands | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - NC - HAN radio diagnostic commands
93 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Import IHD | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Import IHD
94 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Import ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Import ESI
95 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Sync ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Sync ESI
96 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Provision ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Provision ESI
97 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Associate IHD to ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Associate IHD to ESI
98 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Join IHD to ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Join IHD to ESI
99 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Ping IHD via ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Ping IHD via ESI
101 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Unjoin IHD to ESI | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Unjoin IHD to ESI
102 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - HAN secure key establishment | 3-Medium |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - HAN secure key establishment
103 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | HCM - Enroll ESI to HCM program | 3-Medium |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - HCM - Enroll ESI to HCM program
105 | L&G 82-R64 | U3400 R6.4 - NIC3 | 016 - HAN | NC - HAN radio diagnostic commands | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - NC - HAN radio diagnostic commands
93 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Import IHD | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Import IHD
94 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Import ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Import ESI
95 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Sync ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Sync ESI
96 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Provision ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Provision ESI
97 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Associate IHD to ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Associate IHD to ESI
98 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Join IHD to ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Join IHD to ESI
99 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Ping IHD via ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Ping IHD via ESI
101 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Unjoin IHD to ESI | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Unjoin IHD to ESI
102 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - HAN secure key establishment | 3-Medium |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - HAN secure key establishment
103 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | HCM - Enroll ESI to HCM program | 3-Medium |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - HCM - Enroll ESI to HCM program
105 | L&G 82-R64 | U3400 R6.4 - NIC5 | 016 - HAN | NC - HAN radio diagnostic commands | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - NC - HAN radio diagnostic commands
83 | L&G 82-R64 | U3400 R6.4 - NIC3 | 017 - Supply Capacity Control | ESCC Normal Operation - Active Meters | 1-Critical |  | 4556900% | 10:51 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - ESCC Normal Operation - Active Meters
1695 | L&G 82-R64 | U3400 R6.4 - NIC3 | 017 - Supply Capacity Control | ESCC Operation on Export | 1-Critical |  | 4557200% | 17:54 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - ESCC Operation on Export
83 | L&G 82-R64 | U1300 R6.4 - NIC3 | 017 - Supply Capacity Control | ESCC Normal Operation - Active Meters | 1-Critical |  | 4557300% | 16:18 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - ESCC Normal Operation - Active Meters
1695 | L&G 82-R64 | U1300 R6.4 - NIC3 | 017 - Supply Capacity Control | ESCC Operation on Export | 1-Critical |  | 4557300% | 16:42 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - ESCC Operation on Export
83 | L&G 82-R64 | U3400 R6.4 - NIC5 | 017 - Supply Capacity Control | ESCC Normal Operation - Active Meters | 1-Critical |  | 4556900% | 10:51 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - ESCC Normal Operation - Active Meters
1695 | L&G 82-R64 | U3400 R6.4 - NIC5 | 017 - Supply Capacity Control | ESCC Operation on Export | 1-Critical |  | 4557200% | 17:54 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - ESCC Operation on Export
83 | L&G 82-R64 | U1300 R6.4 - NIC5 | 017 - Supply Capacity Control | ESCC Normal Operation - Active Meters | 1-Critical |  | 4557300% | 16:19 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - ESCC Normal Operation - Active Meters
1695 | L&G 82-R64 | U1300 R6.4 - NIC5 | 017 - Supply Capacity Control | ESCC Operation on Export | 1-Critical |  | 4557300% | 16:42 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - ESCC Operation on Export
84 | L&G 82-R64 | U3400 R6.4 - NIC5 | 018 - Security | Meter tamper - terminal cover | 1-Critical |  | 4557500% | 12:33 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Meter tamper - terminal cover
84 | L&G 82-R64 | U3400 R6.4 - NIC3 | 018 - Security | Meter tamper - terminal cover | 1-Critical |  | 4557500% | 12:32 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Meter tamper - terminal cover
84 | L&G 82-R64 | U1300 R6.4 - NIC5 | 018 - Security | Meter tamper - terminal cover | 1-Critical |  | 4557200% | 16:32 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Meter tamper - terminal cover
84 | L&G 82-R64 | U1300 R6.4 - NIC3 | 018 - Security | Meter tamper - terminal cover | 1-Critical |  | 4557200% | 16:30 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Meter tamper - terminal cover
1793 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, no randomisation) | 2-High |  | 4556900% | 15:03 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast - Load contactor connect via broadcast (immediate, no randomisation)
1794 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, randomisation) | 2-High |  | 4556900% | 15:29 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast - Load contactor connect via broadcast (immediate, randomisation)
1795 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (scheduled, no randomisation) | 2-High |  | 4556900% | 15:49 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast - Load contactor connect via broadcast (scheduled, no randomisation)
1796 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation) | 2-High |  | 4557200% | 10:52 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation)
1797 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, randomisation) | 2-High |  | 4557200% | 11:15 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast - Load contactor disconnect via broadcast (immediate, randomisation)
1798 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation) | 2-High |  | 4557200% | 11:42 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation)
129 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 01 - Broadcast Groups - UIQ to meter | 2-High |  | 4556000% | 11:59 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast 01 - Broadcast Groups - UIQ to meter
130 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 02 - Broadcast Groups - meter to UIQ | 2-High |  | 4556000% | 13:33 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast 02 - Broadcast Groups - meter to UIQ
137 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 08 - ESCC opeation via broadcast | 2-High |  | 4556900% | 13:04 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast 08 - ESCC opeation via broadcast
136 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 09 - Load contactor opeation via broadcast | 2-High |  | 4556900% | 14:28 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast 09 - Load contactor opeation via broadcast
1793 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, no randomisation) | 2-High |  | 4556100% | 12:11 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast - Load contactor connect via broadcast (immediate, no randomisation)
1794 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, randomisation) | 2-High |  | 4556100% | 13:11 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast - Load contactor connect via broadcast (immediate, randomisation)
1795 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (scheduled, no randomisation) | 2-High |  | 4556100% | 14:11 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast - Load contactor connect via broadcast (scheduled, no randomisation)
1796 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation) | 2-High |  | 4556500% | 9:42 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation)
1797 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, randomisation) | 2-High |  | 4556500% | 10:12 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast - Load contactor disconnect via broadcast (immediate, randomisation)
1798 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation) | 2-High |  | 4556500% | 10:44 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation)
129 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 01 - Broadcast Groups - UIQ to meter | 2-High |  | 4555500% | 16:51 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast 01 - Broadcast Groups - UIQ to meter
130 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 02 - Broadcast Groups - meter to UIQ | 2-High |  | 4556100% | 11:03 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast 02 - Broadcast Groups - meter to UIQ
137 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 08 - ESCC opeation via broadcast | 2-High |  | 4556500% | 12:02 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast 08 - ESCC opeation via broadcast
136 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 09 - Load contactor opeation via broadcast | 2-High |  | 4556500% | 17:13 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast 09 - Load contactor opeation via broadcast
1793 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, no randomisation) | 2-High |  | 4556900% | 15:04 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast - Load contactor connect via broadcast (immediate, no randomisation)
1794 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, randomisation) | 2-High |  | 4556900% | 15:28 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast - Load contactor connect via broadcast (immediate, randomisation)
1795 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (scheduled, no randomisation) | 2-High |  | 4556900% | 15:49 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast - Load contactor connect via broadcast (scheduled, no randomisation)
1796 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation) | 2-High |  | 4557200% | 10:52 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation)
1797 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, randomisation) | 2-High |  | 4557200% | 11:15 | Failed | Failed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast - Load contactor disconnect via broadcast (immediate, randomisation)
1798 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation) | 2-High |  | 4557200% | 11:42 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation)
129 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 01 - Broadcast Groups - UIQ to meter | 2-High |  | 4556000% | 12:00 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast 01 - Broadcast Groups - UIQ to meter
130 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 02 - Broadcast Groups - meter to UIQ | 2-High |  | 4556000% | 13:33 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast 02 - Broadcast Groups - meter to UIQ
137 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 08 - ESCC opeation via broadcast | 2-High |  | 4556900% | 13:04 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast 08 - ESCC opeation via broadcast
136 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 09 - Load contactor opeation via broadcast | 2-High |  | 4556900% | 14:28 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast 09 - Load contactor opeation via broadcast
1793 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, no randomisation) | 2-High |  | 4556100% | 12:15 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast - Load contactor connect via broadcast (immediate, no randomisation)
1794 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (immediate, randomisation) | 2-High |  | 4556100% | 13:10 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast - Load contactor connect via broadcast (immediate, randomisation)
1795 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor connect via broadcast (scheduled, no randomisation) | 2-High |  | 4556100% | 14:14 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast - Load contactor connect via broadcast (scheduled, no randomisation)
1796 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation) | 2-High |  | 4556500% | 9:43 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation)
1797 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (immediate, randomisation) | 2-High |  | 4558100% | 14:39 | Failed | Failed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast - Load contactor disconnect via broadcast (immediate, randomisation)
1798 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation) | 2-High |  | 4556500% | 10:42 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation)
129 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 01 - Broadcast Groups - UIQ to meter | 2-High |  | 4555500% | 16:37 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast 01 - Broadcast Groups - UIQ to meter
130 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 02 - Broadcast Groups - meter to UIQ | 2-High |  | 4556100% | 11:03 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast 02 - Broadcast Groups - meter to UIQ
137 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 08 - ESCC opeation via broadcast | 2-High |  | 4556500% | 12:03 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast 08 - ESCC opeation via broadcast
136 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 09 - Load contactor opeation via broadcast | 2-High |  | 4556500% | 17:13 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast 09 - Load contactor opeation via broadcast
132 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 04 - Confirm the range of broadcast groups | 2-High |  | 4557300% | 17:08 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - Broadcast 04 - Confirm the range of broadcast groups
132 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 04 - Confirm the range of broadcast groups | 2-High |  | 4557300% | 17:08 | Passed | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC5 - Broadcast 04 - Confirm the range of broadcast groups
132 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 04 - Confirm the range of broadcast groups | 2-High |  | 4556000% | 13:45 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC3 - Broadcast 04 - Confirm the range of broadcast groups
132 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 04 - Confirm the range of broadcast groups | 2-High |  | 4556000% | 13:45 | Passed | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - Broadcast 04 - Confirm the range of broadcast groups
133 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 05 - Broadcast cert upload via netmgr | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Broadcast 05 - Broadcast cert upload via netmgr
134 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 07 - Broadcast cert upload via Network Centre | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Broadcast 07 - Broadcast cert upload via Network Centre
135 | L&G 82-R64 | U3400 R6.4 - NIC5 | 020 - Broadcast | Broadcast 06 - Broadcast cert upload via FSU | 2-High |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - Broadcast 06 - Broadcast cert upload via FSU
133 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 05 - Broadcast cert upload via netmgr | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Broadcast 05 - Broadcast cert upload via netmgr
134 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 07 - Broadcast cert upload via Network Centre | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Broadcast 07 - Broadcast cert upload via Network Centre
135 | L&G 82-R64 | U3400 R6.4 - NIC3 | 020 - Broadcast | Broadcast 06 - Broadcast cert upload via FSU | 2-High |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - Broadcast 06 - Broadcast cert upload via FSU
133 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 05 - Broadcast cert upload via netmgr | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Broadcast 05 - Broadcast cert upload via netmgr
134 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 07 - Broadcast cert upload via Network Centre | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Broadcast 07 - Broadcast cert upload via Network Centre
135 | L&G 82-R64 | U1300 R6.4 - NIC5 | 020 - Broadcast | Broadcast 06 - Broadcast cert upload via FSU | 2-High |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - Broadcast 06 - Broadcast cert upload via FSU
133 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 05 - Broadcast cert upload via netmgr | 2-High |  | 4555900% | 17:13 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Broadcast 05 - Broadcast cert upload via netmgr
134 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 07 - Broadcast cert upload via Network Centre | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Broadcast 07 - Broadcast cert upload via Network Centre
135 | L&G 82-R64 | U1300 R6.4 - NIC3 | 020 - Broadcast | Broadcast 06 - Broadcast cert upload via FSU | 2-High |  | 4555900% | 17:14 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - Broadcast 06 - Broadcast cert upload via FSU
1802 | L&G 82-R64 | U3400 R6.4 - NIC5 | HSM Cert Refresh | HCM - Send message to IHD | 3-Medium |  | 4557900% | 15:06 | RBT | Passed | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | Executed | Done | U3400 R6.4 - NIC5 - HCM - Send message to IHD
1802 | L&G 82-R64 | U3400 R6.4 - NIC3 | HSM Cert Refresh | HCM - Send message to IHD | 3-Medium |  | 4557900% | 15:07 | RBT | Blocked | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | No Run | Blocked | U3400 R6.4 - NIC3 - HCM - Send message to IHD
1802 | L&G 82-R64 | U1300 R6.4 - NIC5 | HSM Cert Refresh | HCM - Send message to IHD | 3-Medium | No appropriate meter with HAN certificate but passed on NIC320 meter | 4558000% | 14:33 | RBT | RBT | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - HCM - Send message to IHD
1802 | L&G 82-R64 | U1300 R6.4 - NIC3 | HSM Cert Refresh | HCM - Send message to IHD | 3-Medium |  | 4558000% | 13:46 | RBT | Passed | knjuguna(Kamau Njuguna) | knjuguna(Kamau Njuguna) | Executed | Done | U1300 R6.4 - NIC3 - HCM - Send message to IHD
1722 | L&G 82-R64 | U3400 R6.4 - NIC5 | PQ Polling | 02 L&G PQ Configuration - Remote Enable-Disable | 1-Critical |  | 4555900% | 17:18 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - 02 L&G PQ Configuration - Remote Enable-Disable
1722 | L&G 82-R64 | U3400 R6.4 - NIC3 | PQ Polling | 02 L&G PQ Configuration - Remote Enable-Disable | 1-Critical |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - 02 L&G PQ Configuration - Remote Enable-Disable
1722 | L&G 82-R64 | U1300 R6.4 - NIC5 | PQ Polling | 02 L&G PQ Configuration - Remote Enable-Disable | 1-Critical |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - 02 L&G PQ Configuration - Remote Enable-Disable
1722 | L&G 82-R64 | U1300 R6.4 - NIC3 | PQ Polling | 02 L&G PQ Configuration - Remote Enable-Disable | 1-Critical |  | 4555900% | 17:12 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - 02 L&G PQ Configuration - Remote Enable-Disable
1723 | L&G 82-R64 | U1300 R6.4 - NIC3 | PQ Polling | 03 L&G PQ Polling - Data Integrity | 1-Critical |  | 4555900% | 17:12 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC3 - 03 L&G PQ Polling - Data Integrity
1723 | L&G 82-R64 | U1300 R6.4 - NIC5 | PQ Polling | 03 L&G PQ Polling - Data Integrity | 1-Critical |  | 4555900% | 17:15 | RBT | RBT | mkalra(Manoj Kalra) | knjuguna(Kamau Njuguna) | RBT | Done | U1300 R6.4 - NIC5 - 03 L&G PQ Polling - Data Integrity
1723 | L&G 82-R64 | U3400 R6.4 - NIC3 | PQ Polling | 03 L&G PQ Polling - Data Integrity | 1-Critical |  | 4555900% | 17:16 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC3 - 03 L&G PQ Polling - Data Integrity
1723 | L&G 82-R64 | U3400 R6.4 - NIC5 | PQ Polling | 03 L&G PQ Polling - Data Integrity | 1-Critical |  | 4555900% | 17:17 | RBT | RBT | mkalra(Manoj Kalra) | mkalra(Manoj Kalra) | RBT | Done | U3400 R6.4 - NIC5 - 03 L&G PQ Polling - Data Integrity

## 2024 - L&G R64 Pivot
TC Status | Status | [10 empty] | Make sure this is only sorted by Test Name
| knjuguna(Kamau Njuguna) |  |  |  | knjuguna(Kamau Njuguna) Total | mkalra(Manoj Kalra) |  |  |  | mkalra(Manoj Kalra) Total | Grand Total | Count of Test: Test Name: | Column Labels
Test Cycle | Done | Unfinished | - | N/A |  | Done | - | N/A | Blocked |  |  | Row Labels | U1300 R6.4 - NIC3 | U1300 R6.4 - NIC5 | U3400 R6.4 - NIC3 | U3400 R6.4 - NIC5 | Grand Total | Remarks
L&G 82-R64 | 169 | 4 | 1 | 6 | 180 | 171 | 3 | 6 | 2 | 182 | 362 | 01 Meter Time synchronisation to NIC - forward within interval (Auto) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
Grand Total | 169 | 4 | 1 | 6 | 180 | 171 | 3 | 6 | 2 | 182 | 362 | 02 L&G PQ Configuration - Remote Enable-Disable | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | 02 Meter Time synchronisation to NIC - forward within interval (Force) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | 03 L&G PQ Polling - Data Integrity | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | 03 Meter Time synchronisation to NIC - backward within interval (Auto) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
TC Status | Status | [10 empty] | 04 Meter Time synchronisation to NIC - backward within interval (Force) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
| knjuguna(Kamau Njuguna) |  |  |  | knjuguna(Kamau Njuguna) Total | mkalra(Manoj Kalra) |  |  |  | mkalra(Manoj Kalra) Total | Grand Total | 05 Meter Time synchronisation to NIC - forward crossing interval (Auto) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
Test Cycle | Done | Unfinished | - | N/A |  | Done | - | N/A | Blocked |  |  | 06 Meter Time synchronisation to NIC - forward crossing interval (Force) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
L&G 82-R64 | 46.69% | 1.105% | 0.2762% | 1.657% | 49.72% | 47.24% | 0.8287% | 1.657% | 0.5525% | 50.28% | 100% | 07 Meter Time synchronisation to NIC - backward crossing interval (Auto) | 1 | 1 | 1 | 1 | 4
Grand Total | 46.69% | 1.105% | 0.2762% | 1.657% | 49.72% | 47.24% | 0.8287% | 1.657% | 0.5525% | 50.28% | 100% | 08 Meter Time synchronisation to NIC - backward crossing interval (Force) | 1 | 1 | 1 | 1 | 4
[12 empty] | AMM - On Demand Read - C1219 Read | 1 | 1 | 1 | 1 | 4
[12 empty] | AMM - On Demand Read - Interval | 1 | 1 | 1 | 1 | 4
[12 empty] | AMM - On Demand Read - New Data | 1 | 1 | 1 | 1 | 4
[12 empty] | AMM - On Demand Read - NIC Event Log | 1 | 1 | 1 | 1 | 4
[12 empty] | AMM - On Demand Read - Register | 1 | 1 | 1 | 1 | 4
Target Cycle: | L&G 82-R64 | [10 empty] | AMM - On Demand Read - Stored Self Read | 1 | 1 | 1 | 1 | 4
[12 empty] | Auto-Disconnect - Disabled | 1 | 1 | 1 | 1 | 4
Count of Done | Column Labels | [10 empty] | Auto-Disconnect - Enabled | 1 | 1 | 1 | 1 | 4
Row Labels | 1-Critical | 2-High | 3-Medium | 4-Low | Grand Total | [6 empty] | Auto-Disconnect - Override For NAP (L+G) | 1 | 1 | 1 | 1 | 4
Done | 174 | 139 | 23 | 4 | 340 | [6 empty] | Auto-Disconnect - Remote Lockout | 1 | 1 | 1 | 1 | 4
Unfinished | 3 | 1 |  |  | 4 | [6 empty] | Boost operation - Disabled | 1 | 1 | 1 | 1 | 4
- | 4 |  |  |  | 4 | [6 empty] | Boost operation - Enabled - Boost (Boost Duration) minutes | 1 | 1 | 1 | 1 | 4
N/A | 8 |  | 4 |  | 12 | [6 empty] | Boost Primacy - Boost time longer than LC override | 1 | 1 | 1 | 1 | 4 | Execute at the same time
Blocked | 1 |  | 1 |  | 2 | [6 empty] | Boost Primacy - Disabled | 1 | 1 | 1 | 1 | 4 | Execute at the same time
Grand Total | 190 | 140 | 28 | 4 | 362 | [6 empty] | Boost Primacy - Enable-Disable | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast - Load contactor connect via broadcast (immediate, no randomisation) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast - Load contactor connect via broadcast (immediate, randomisation) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast - Load contactor connect via broadcast (scheduled, no randomisation) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast - Load contactor disconnect via broadcast (immediate, no randomisation) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast - Load contactor disconnect via broadcast (immediate, randomisation) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast - Load contactor disconnect via broadcast (scheduled, no randomisation) | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast 01 - Broadcast Groups - UIQ to meter | 1 | 1 | 1 | 1 | 4 | Execute at the same time
[12 empty] | Broadcast 02 - Broadcast Groups - meter to UIQ | 1 | 1 | 1 | 1 | 4
[12 empty] | Broadcast 04 - Confirm the range of broadcast groups | 1 | 1 | 1 | 1 | 4
Status: | (All) | [10 empty] | Broadcast 05 - Broadcast cert upload via netmgr | 1 | 1 | 1 | 1 | 4
Target Cycle: | (All) | [10 empty] | Broadcast 06 - Broadcast cert upload via FSU | 1 | 1 | 1 | 1 | 4
[12 empty] | Broadcast 07 - Broadcast cert upload via Network Centre | 1 | 1 | 1 | 1 | 4
Count of Status: | Tester | [10 empty] | Broadcast 08 - ESCC opeation via broadcast | 1 | 1 | 1 | 1 | 4
Exec Date | knjuguna(Kamau Njuguna) | (blank) | mkalra(Manoj Kalra) | Grand Total | [7 empty] | Broadcast 09 - Load contactor opeation via broadcast | 1 | 1 | 1 | 1 | 4
4555500% | 10 |  | 8 | 18 | [7 empty] | ESCC Normal Operation - Active Meters | 1 | 1 | 1 | 1 | 4
4555800% | 2 |  |  | 2 | [7 empty] | ESCC Operation on Export | 1 | 1 | 1 | 1 | 4
4555900% | 5 |  | 92 | 97 | [7 empty] | FWU meter firmware upgrade - (seedingpercent) percent seeded - Interrupted | 1 | 1 | 1 | 1 | 4
4556000% |  |  | 14 | 14 | [7 empty] | FWU meter firmware upgrade - (seedingpercent) percent seeded - Uninterrupted | 1 | 1 | 1 | 1 | 4
4556100% | 8 |  | 5 | 13 | [7 empty] | HCM - Import ESI | 1 | 1 | 1 | 1 | 4
4556500% | 14 |  | 10 | 24 | [7 empty] | HCM - Import IHD | 1 | 1 | 1 | 1 | 4
4556600% | 3 |  | 10 | 13 | [7 empty] | HCM - Provision ESI | 1 | 1 | 1 | 1 | 4
4556700% |  |  | 8 | 8 | [7 empty] | HCM - Sync ESI | 1 | 1 | 1 | 1 | 4
4556800% | 8 |  | 4 | 12 | [7 empty] | HCM - Associate IHD to ESI | 1 | 1 | 1 | 1 | 4
4556900% | 14 |  | 14 | 28 | [7 empty] | HCM - Display meter consumption on IHD | 1 | 1 | 1 | 1 | 4
4557200% | 12 |  | 18 | 30 | [7 empty] | HCM - Enroll ESI to HCM program | 1 | 1 | 1 | 1 | 4
4557300% | 10 |  | 4 | 14 | [7 empty] | HCM - HAN secure key establishment | 1 | 1 | 1 | 1 | 4
4557400% | 12 |  | 9 | 21 | [7 empty] | HCM - Join IHD to ESI | 1 | 1 | 1 | 1 | 4
4557500% | 5 |  | 5 | 10 | [7 empty] | HCM - Ping IHD via ESI | 1 | 1 | 1 | 1 | 4
4557600% | 10 |  | 6 | 16 | [7 empty] | HCM - Send message to IHD | 1 | 1 | 1 | 1 | 4
4557900% | 8 |  | 14 | 22 | [7 empty] | HCM - Support for 2E meters metering cluster | 1 | 1 | 1 | 1 | 4
4558000% | 12 |  | 5 | 17 | [7 empty] | HCM - Unjoin IHD to ESI | 1 | 1 | 1 | 1 | 4
4558100% | 3 |  |  | 3 | [7 empty] | L&G_LP_Enable | 1 | 1 | 1 | 1 | 4
(blank) | [11 empty] | Loss of phase supply on 3-phase meters |  |  | 1 | 1 | 2
Grand Total | 136 |  | 226 | 362 | [7 empty] | Loss of supply - threshold | 1 | 1 | 1 | 1 | 4
[12 empty] | Loss of supply - Verify last gasp for multiple meter outage | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Accuracy | 1 | 1 | 1 | 1 | 4
| Test: Test Priority: | (Multiple Items) | [9 empty] | Meter Data Integrity - AMM export | 1 | 1 | 1 | 1 | 4
| Target Cycle: | (All) | [9 empty] | Meter Data Integrity - EBQK | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Data Integrity - Meter to UIQ (Full) | 1 | 1 | 1 | 1 | 4
| Count of Status: | Column Labels | [9 empty] | Meter Data Integrity - Meter to UIQ (Sanity) | 1 | 1 | 1 | 1 | 4
| Row Labels | Failed | Passed | Not Completed | RBT | Deferred | N/A | Blocked | Grand Total |  |  | Meter display - register resolution | 1 | 1 | 1 | 1 | 4
| knjuguna(Kamau Njuguna) | 17 | 102 | 4 | 50 | 1 | 6 |  | 180 |  |  | Meter firmware audit | 1 | 1 | 1 | 1 | 4
| mkalra(Manoj Kalra) | 10 | 112 |  | 49 | 3 | 6 | 2 | 182 |  |  | Meter load contactor - remote override (close) | 1 | 1 | 1 | 1 | 4
| Grand Total | 27 | 214 | 4 | 99 | 4 | 12 | 2 | 362 |  |  | Meter load contactor - remote override (open) | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter load contactor - switching schedule 5-on-5-off | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Program - export events | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Program - NIC program seal | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Program - Partial programming (Remote) | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Program - Remote 1 - Load a full meter program (New Meter Program in UIQ) | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter Program - Remote 4 - Load a full meter program (Meter Program exists in UIQ) | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter program audit | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter state transitions - New to xxx to Active | 2 | 2 | 2 | 2 | 8
[12 empty] | Meter supply contactor - Arm Remotely | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter supply contactor - Remote Lockout | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter supply contactor connect disconnect - local | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter supply contactor connect disconnect - remote | 1 | 1 | 1 | 1 | 4
[12 empty] | Meter tamper - terminal cover | 1 | 1 | 1 | 1 | 4
[12 empty] | NC - HAN radio diagnostic commands | 1 | 1 | 1 | 1 | 4
[12 empty] | Over temperature event - L&G meters | 1 | 1 | 1 | 1 | 4
[12 empty] | QoS - Low PF detection | 1 | 1 | 1 | 1 | 4
[12 empty] | QoS - Overvoltage and Undervoltage | 1 | 1 | 1 | 1 | 4
[12 empty] | QoS - Voltage failure detection | 1 | 1 | 1 | 1 | 4
[12 empty] | Reloading RMA meters into UIQ | 2 | 2 | 2 | 2 | 8
[12 empty] | SIQ Profile Sanity Check | 1 | 1 | 1 | 1 | 4
[12 empty] | Grand Total | 90 | 90 | 91 | 91 | 362

## 2024 - L&G R64 Tracking
|  |  | Actual Resource Availability |  |  | Planned Resource Availability |  |  | Planned Velocity |  |  | Delta Velocity |  |  |  |  | Actual Velocity |  |  |  | Running Average Velocity |  |  | Daily Velocity |  |  |  | Total Velocity |  |  | Projection |  |  |  |  | # of testers = 2 | Target Finish Date | 4558200% | Actual Resource Availability (Based on if testing that day) |  |  |  | Running Average Velocity (Based on if testing that day)
Day | Date | Working Day | Kamau | Manoj | Leonard | Kamau | Manoj | Leonard | Kamau | Manoj | Leonard | Kamau | Manoj | Leonard | Date | Working Day | knjuguna(Kamau Njuguna) | mkalra(Manoj Kalra) | ljarillas(Leonard Jarillas) | Target | knjuguna(Kamau Njuguna) | mkalra(Manoj Kalra) | ljarillas(Leonard Jarillas) | Date | Planned | Actual | Average | Date | Planned | Actual | Date | 5D Running Average | 5D Running Average / Resource | Average/Resource | Projected Finish | Needed velocity | Needed velocity / tester | Notes | Kamau | Manoj | Leonard | Date | knjuguna(Kamau Njuguna) | mkalra(Manoj Kalra) | ljarillas(Leonard Jarillas)
Fri | 2024-09-20 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 2 | 0 | 0 | 2024-09-20 | 1 | 10 | 8 | 0 | 8 | 10 | 8 | #DIV/0! | 2024-09-20 | 16 | 18 | 18 | 2024-09-20 | 274 | 361 | 2024-09-20 |  |  | 9 |  | 20.0556 | 10.0278 |  | 1 | 1 | 0 | 2024-09-20 | 10 | 8 | #DIV/0!
Sat | 2024-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-21 | 0 | 0 | 0 | 0 | 8 | 10 | 8 | #DIV/0! | 2024-09-21 | 0 | 0 | 18 | 2024-09-21 | 274 | 361 | 2024-09-21 |  |  | 0 |  | 21.2353 | 10.6176 |  | 0 | 0 | 0 | 2024-09-21 | 10 | 8 | #DIV/0!
Sun | 2024-09-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-22 | 0 | 0 | 0 | 0 | 8 | 10 | 8 | #DIV/0! | 2024-09-22 | 0 | 0 | 18 | 2024-09-22 | 274 | 361 | 2024-09-22 |  |  | 0 |  | 21.2353 | 10.6176 |  | 0 | 0 | 0 | 2024-09-22 | 10 | 8 | #DIV/0!
Mon | 2024-09-23 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -6 | -8 | 0 | 2024-09-23 | 1 | 2 | 0 | 0 | 8 | 6 | 4 | #DIV/0! | 2024-09-23 | 16 | 2 | 10 | 2024-09-23 | 258 | 359 | 2024-09-23 |  |  | 1 |  | 21.1176 | 10.5588 |  | 1 | 0 | 0 | 2024-09-23 | 6 | 8 | #DIV/0!
Tue | 2024-09-24 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -3 | 84 | 0 | 2024-09-24 | 1 | 5 | 92 | 0 | 8 | 5.6667 | 33.3333 | #DIV/0! | 2024-09-24 | 16 | 97 | 39 | 2024-09-24 | 242 | 262 | 2024-09-24 | 39 | 19.5 | 48.5 | 2024-10-03 09:43 | 16.375 | 8.1875 |  | 1 | 1 | 0 | 2024-09-24 | 5.6667 | 50 | #DIV/0!
Wed | 2024-09-25 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -8 | 6 | 0 | 2024-09-25 | 1 | 0 | 14 | 0 | 8 | 5.6667 | 28.5 | #DIV/0! | 2024-09-25 | 16 | 14 | 34.1667 | 2024-09-25 | 226 | 248 | 2024-09-25 | 37.6667 | 22.6 | 14 | 2024-10-04 05:13 | 16.5333 | 8.2667 |  | 0 | 1 | 0 | 2024-09-25 | 5.6667 | 38 | #DIV/0!
Thu | 2024-09-26 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 0 | -3 | 0 | 2024-09-26 | 1 | 8 | 5 | 0 | 8 | 6.25 | 23.8 | #DIV/0! | 2024-09-26 | 16 | 13 | 30.05 | 2024-09-26 | 210 | 235 | 2024-09-26 | 31.5 | 18 | 6.5 | 2024-10-06 10:40 | 16.7857 | 8.3929 |  | 1 | 1 | 0 | 2024-09-26 | 6.25 | 29.75 | #DIV/0!
Fri | 2024-09-27 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-27 | 0 | 0 | 0 | 0 | 8 | 6.25 | 23.8 | #DIV/0! | 2024-09-27 | 0 | 0 | 30.05 | 2024-09-27 | 210 | 235 | 2024-09-27 | 31.5 | 18 | 0 | 2024-10-07 10:40 | 18.0769 | 9.0385 |  | 0 | 0 | 0 | 2024-09-27 | 6.25 | 29.75 | #DIV/0!
Sat | 2024-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-28 | 0 | 0 | 0 | 0 | 8 | 6.25 | 23.8 | #DIV/0! | 2024-09-28 | 0 | 0 | 30.05 | 2024-09-28 | 210 | 235 | 2024-09-28 | 41.3333 | 24.8 | 0 | 2024-10-05 23:02 | 18.0769 | 9.0385 |  | 0 | 0 | 0 | 2024-09-28 | 6.25 | 29.75 | #DIV/0!
Sun | 2024-09-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-29 | 0 | 0 | 0 | 0 | 8 | 6.25 | 23.8 | #DIV/0! | 2024-09-29 | 0 | 0 | 30.05 | 2024-09-29 | 210 | 235 | 2024-09-29 | 13.5 | 9 | 0 | 2024-10-23 08:53 | 18.0769 | 9.0385 |  | 0 | 0 | 0 | 2024-09-29 | 6.25 | 29.75 | #DIV/0!
Mon | 2024-09-30 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 6 | 2 | 0 | 2024-09-30 | 1 | 14 | 10 | 0 | 8 | 7.8 | 21.5 | #DIV/0! | 2024-09-30 | 16 | 24 | 29.3 | 2024-09-30 | 194 | 211 | 2024-09-30 | 18.5 | 9.25 | 12 | 2024-10-15 23:13 | 16.2308 | 8.1154 |  | 1 | 1 | 0 | 2024-09-30 | 7.8 | 25.8 | #DIV/0!
Tue | 2024-10-01 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -5 | 2 | 0 | 2024-10-01 | 1 | 3 | 10 | 0 | 8 | 7 | 19.8571 | #DIV/0! | 2024-10-01 | 16 | 13 | 26.8571 | 2024-10-01 | 178 | 198 | 2024-10-01 | 18.5 | 9.25 | 6.5 | 2024-10-15 23:37 | 16.5 | 8.25 |  | 1 | 1 | 0 | 2024-10-01 | 7 | 23.1667 | #DIV/0!
Wed | 2024-10-02 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -8 | 0 | 0 | 2024-10-02 | 1 | 0 | 8 | 0 | 8 | 7 | 18.375 | #DIV/0! | 2024-10-02 | 16 | 8 | 25.375 | 2024-10-02 | 162 | 190 | 2024-10-02 | 15 | 9 | 8 | 2024-10-19 17:36 | 17.2727 | 8.6364 |  | 0 | 1 | 0 | 2024-10-02 | 7 | 21 | #DIV/0!
Thu | 2024-10-03 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 0 | -4 | 0 | 2024-10-03 | 1 | 8 | 4 | 0 | 8 | 7.1429 | 16.7778 | #DIV/0! | 2024-10-03 | 16 | 12 | 23.9206 | 2024-10-03 | 146 | 178 | 2024-10-03 | 14.25 | 8.1429 | 6 | 2024-10-20 11:42 | 17.8 | 8.9 |  | 1 | 1 | 0 | 2024-10-03 | 7.1429 | 18.875 | #DIV/0!
Fri | 2024-10-04 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 6 | 6 | 0 | 2024-10-04 | 1 | 14 | 14 | 0 | 8 | 8 | 16.5 | #DIV/0! | 2024-10-04 | 16 | 28 | 24.5 | 2024-10-04 | 130 | 150 | 2024-10-04 | 17 | 9.4444 | 14 | 2024-10-16 08:28 | 16.6667 | 8.3333 |  | 1 | 1 | 0 | 2024-10-04 | 8 | 18.3333 | #DIV/0!
Sat | 2024-10-05 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-05 | 0 | 0 | 0 | 0 | 8 | 8 | 16.5 | #DIV/0! | 2024-10-05 | 0 | 0 | 24.5 | 2024-10-05 | 130 | 150 | 2024-10-05 | 15.25 | 8.7143 | 0 | 2024-10-18 18:30 | 18.75 | 9.375 |  | 0 | 0 | 0 | 2024-10-05 | 8 | 18.3333 | #DIV/0!
Sun | 2024-10-06 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-06 | 0 | 0 | 0 | 0 | 8 | 8 | 16.5 | #DIV/0! | 2024-10-06 | 0 | 0 | 24.5 | 2024-10-06 | 130 | 150 | 2024-10-06 | 16 | 9.6 | 0 | 2024-10-19 03:00 | 18.75 | 9.375 |  | 0 | 0 | 0 | 2024-10-06 | 8 | 18.3333 | #DIV/0!
Mon | 2024-10-07 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 4 | 8 | 0 | 2024-10-07 | 1 | 12 | 16 | 0 | 8 | 8.4444 | 16.4545 | #DIV/0! | 2024-10-07 | 16 | 28 | 24.899 | 2024-10-07 | 114 | 122 | 2024-10-07 | 22.6667 | 11.3333 | 14 | 2024-10-14 12:51 | 15.25 | 7.625 |  | 1 | 1 | 0 | 2024-10-07 | 8.4444 | 18.1 | #DIV/0!
Tue | 2024-10-08 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 2 | -4 | 0 | 2024-10-08 | 1 | 10 | 4 | 0 | 8 | 8.6 | 15.4167 | #DIV/0! | 2024-10-08 | 16 | 14 | 24.0167 | 2024-10-08 | 98 | 108 | 2024-10-08 | 23.3333 | 11.6667 | 7 | 2024-10-14 11:31 | 15.4286 | 7.7143 |  | 1 | 1 | 0 | 2024-10-08 | 8.6 | 16.8182 | #DIV/0!
Wed | 2024-10-09 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 0 | -1 | 0 | 2024-10-09 | 1 | 8 | 7 | 0 | 8 | 8.5455 | 14.7692 | #DIV/0! | 2024-10-09 | 16 | 15 | 23.3147 | 2024-10-09 | 82 | 93 | 2024-10-09 | 19 | 9.5 | 7.5 | 2024-10-15 20:28 | 15.5 | 7.75 |  | 1 | 1 | 0 | 2024-10-09 | 8.5455 | 16 | #DIV/0!
Thu | 2024-10-10 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -4 | -3 | 0 | 2024-10-10 | 1 | 4 | 5 | 0 | 8 | 8.1667 | 14.0714 | #DIV/0! | 2024-10-10 | 16 | 9 | 22.2381 | 2024-10-10 | 66 | 84 | 2024-10-10 | 16.5 | 8.25 | 4.5 | 2024-10-17 03:03 | 16.8 | 8.4 |  | 1 | 1 | 0 | 2024-10-10 | 8.1667 | 15.1538 | #DIV/0!
Fri | 2024-10-11 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 0 | 2024-10-11 | 1 | 10 | 4 | 0 | 8 | 8.3077 | 13.4 | #DIV/0! | 2024-10-11 | 0 | 14 | 21.7077 | 2024-10-11 | 66 | 70 | 2024-10-11 | 16 | 8 | 7 | 2024-10-17 03:00 | 17.5 | 8.75 |  | 1 | 1 | 0 | 2024-10-11 | 8.3077 | 14.3571 | #DIV/0!
Sat | 2024-10-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-12 | 0 | 0 | 0 | 0 | 8 | 8.3077 | 13.4 | #DIV/0! | 2024-10-12 | 0 | 0 | 21.7077 | 2024-10-12 | 66 | 70 | 2024-10-12 | 13 | 6.5 | 0 | 2024-10-19 12:55 | 23.3333 | 11.6667 |  | 0 | 0 | 0 | 2024-10-12 | 8.3077 | 14.3571 | #DIV/0!
Sun | 2024-10-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-13 | 0 | 0 | 0 | 0 | 8 | 8.3077 | 13.4 | #DIV/0! | 2024-10-13 | 0 | 0 | 21.7077 | 2024-10-13 | 66 | 70 | 2024-10-13 | 12.6667 | 6.3333 | 0 | 2024-10-20 17:41 | 23.3333 | 11.6667 |  | 0 | 0 | 0 | 2024-10-13 | 8.3077 | 14.3571 | #DIV/0!
Mon | 2024-10-14 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 10 | 0 | 2024-10-14 | 1 | 7 | 10 | 0 | 8 | 8.2143 | 13.1875 | #DIV/0! | 2024-10-14 | 0 | 17 | 21.4018 | 2024-10-14 | 66 | 53 | 2024-10-14 | 13.3333 | 6.6667 | 8.5 | 2024-10-19 13:34 | 17.6667 | 8.8333 |  | 1 | 1 | 0 | 2024-10-14 | 8.2143 | 14.0667 | #DIV/0!
Tue | 2024-10-15 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | 0 | -4 | 0 | 2024-10-15 | 1 | 8 | 4 | 0 | 8 | 8.2 | 12.6471 | #DIV/0! | 2024-10-15 | 16 | 12 | 20.8471 | 2024-10-15 | 50 | 41 | 2024-10-15 | 14.3333 | 7.1667 | 6 | 2024-10-19 00:07 | 20.5 | 10.25 |  | 1 | 1 | 0 | 2024-10-15 | 8.2 | 13.4375 | #DIV/0!
Wed | 2024-10-16 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -6 | -8 | 0 | 2024-10-16 | 1 | 2 | 0 | 0 | 8 | 7.8125 | 12.6471 | #DIV/0! | 2024-10-16 | 16 | 2 | 20.4596 | 2024-10-16 | 34 | 39 | 2024-10-16 | 10.3333 | 6.2 | 2 | 2024-10-21 06:49 | 39 | 19.5 |  | 1 | 0 | 0 | 2024-10-16 | 7.8125 | 13.4375 | #DIV/0!
Thu | 2024-10-17 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-17 | 1 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-17 | 16 | 0 | 19.2974 | 2024-10-17 | 18 | 39 | 2024-10-17 | 7.75 | 4.4286 | 0 | 2024-10-24 01:05 | #DIV/0! | #DIV/0! |  | 0 | 0 | 0 | 2024-10-17 | 7.8125 | 13.4375 | #DIV/0!
Fri | 2024-10-18 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-18 | 1 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-18 | 16 | 0 | 19.2974 | 2024-10-18 | 2 | 39 | 2024-10-18 | 6.2 | 4.4286 | 0 | 2024-10-26 19:21 | -13 | -6.5 |  | 0 | 0 | 0 | 2024-10-18 | 7.8125 | 13.4375 | #DIV/0!
Sat | 2024-10-19 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-19 | 0 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-19 | 0 | 0 | 19.2974 | 2024-10-19 | 2 | 39 | 2024-10-19 | 3.5 | 2.8 | 0 | 2024-11-03 14:24 | -13 | -6.5 |  | 0 | 0 | 0 | 2024-10-19 | 7.8125 | 13.4375 | #DIV/0!
Sun | 2024-10-20 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-20 | 0 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-20 | 0 | 0 | 19.2974 | 2024-10-20 | 2 | 39 | 2024-10-20 | 0.66667 | 0.66667 | 0 | 2025-01-09 21:36 | -13 | -6.5 |  | 0 | 0 | 0 | 2024-10-20 | 7.8125 | 13.4375 | #DIV/0!
Mon | 2024-10-21 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-21 | 1 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-21 | 0 | 0 | 19.2974 | 2024-10-21 | 2 | 39 | 2024-10-21 | 0 | 0 | 0 | 2025-01-09 21:36 | -9.75 | -4.875 |  | 0 | 0 | 0 | 2024-10-21 | 7.8125 | 13.4375 | #DIV/0!
Tue | 2024-10-22 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-22 | 1 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-22 | 16 | 0 | 19.2974 | 2024-10-22 | -14 | 39 | 2024-10-22 | 0 | #DIV/0! | 0 | 2025-01-09 21:36 | -7.8 | -3.9 |  | 0 | 0 | 0 | 2024-10-22 | 7.8125 | 13.4375 | #DIV/0!
Wed | 2024-10-23 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-23 | 1 | 0 | 0 | 0 | 8 | 7.3529 | 11.9444 | #DIV/0! | 2024-10-23 | 16 | 0 | 19.2974 | 2024-10-23 | -30 | 39 | 2024-10-23 | 0 | #DIV/0! | 0 | 2025-01-09 21:36 | -6.5 | -3.25 |  | 0 | 0 | 0 | 2024-10-23 | 7.8125 | 13.4375 | #DIV/0!
Thu | 2024-10-24 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -4 | -5 | 0 | 2024-10-24 | 1 | 4 | 3 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-24 | 16 | 7 | 19.6993 | 2024-10-24 | -46 | 32 | 2024-10-24 | 1.75 | #DIV/0! | 0 | 2024-11-18 14:24 | -4.5714 | -2.2857 |  | 1 | 1 | 0 | 2024-10-24 | 7.5882 | 12.8235 | #DIV/0!
Fri | 2024-10-25 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-25 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-25 | 16 | 0 | 19.6993 | 2024-10-25 | -62 | 32 | 2024-10-25 | 1.4 | #DIV/0! | 0 | 2024-11-26 | -4 | -2 |  | 0 | 0 | 0 | 2024-10-25 | 7.5882 | 12.8235 | #DIV/0!
Sat | 2024-10-26 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-26 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-26 | 0 | 0 | 19.6993 | 2024-10-26 | -62 | 32 | 2024-10-26 | 1.75 | #DIV/0! | 0 | 2024-11-20 14:24 | -4 | -2 |  | 0 | 0 | 0 | 2024-10-26 | 7.5882 | 12.8235 | #DIV/0!
Sun | 2024-10-27 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-27 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-27 | 0 | 0 | 19.6993 | 2024-10-27 | -62 | 32 | 2024-10-27 | 2.3333 | #DIV/0! | 0 | 2024-11-15 04:48 | -4 | -2 |  | 0 | 0 | 0 | 2024-10-27 | 7.5882 | 12.8235 | #DIV/0!
Mon | 2024-10-28 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-28 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-28 | 16 | 0 | 19.6993 | 2024-10-28 | -78 | 32 | 2024-10-28 | 2.3333 | #DIV/0! | 0 | 2024-11-16 04:48 | -3.5556 | -1.7778 |  | 0 | 0 | 0 | 2024-10-28 | 7.5882 | 12.8235 | #DIV/0!
Tue | 2024-10-29 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-29 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-29 | 16 | 0 | 19.6993 | 2024-10-29 | -94 | 32 | 2024-10-29 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -3.2 | -1.6 |  | 0 | 0 | 0 | 2024-10-29 | 7.5882 | 12.8235 | #DIV/0!
Wed | 2024-10-30 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-30 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-30 | 16 | 0 | 19.6993 | 2024-10-30 | -110 | 32 | 2024-10-30 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.9091 | -1.4545 |  | 0 | 0 | 0 | 2024-10-30 | 7.5882 | 12.8235 | #DIV/0!
Thu | 2024-10-31 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-10-31 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-10-31 | 16 | 0 | 19.6993 | 2024-10-31 | -126 | 32 | 2024-10-31 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.6667 | -1.3333 |  | 0 | 0 | 0 | 2024-10-31 | 7.5882 | 12.8235 | #DIV/0!
Fri | 2024-11-01 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-01 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-01 | 16 | 0 | 19.6993 | 2024-11-01 | -142 | 32 | 2024-11-01 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.4615 | -1.2308 |  | 0 | 0 | 0 | 2024-11-01 | 7.5882 | 12.8235 | #DIV/0!
Sat | 2024-11-02 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-02 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-02 | 0 | 0 | 19.6993 | 2024-11-02 | -142 | 32 | 2024-11-02 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.4615 | -1.2308 |  | 0 | 0 | 0 | 2024-11-02 | 7.5882 | 12.8235 | #DIV/0!
Sun | 2024-11-03 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-03 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-03 | 0 | 0 | 19.6993 | 2024-11-03 | -142 | 32 | 2024-11-03 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.4615 | -1.2308 |  | 0 | 0 | 0 | 2024-11-03 | 7.5882 | 12.8235 | #DIV/0!
Mon | 2024-11-04 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-04 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-04 | 16 | 0 | 19.6993 | 2024-11-04 | -158 | 32 | 2024-11-04 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.2857 | -1.1429 |  | 0 | 0 | 0 | 2024-11-04 | 7.5882 | 12.8235 | #DIV/0!
Tue | 2024-11-05 | 0 |  |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-05 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-05 | 0 | 0 | 19.6993 | 2024-11-05 | -158 | 32 | 2024-11-05 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.2857 | -1.1429 |  | 0 | 0 | 0 | 2024-11-05 | 7.5882 | 12.8235 | #DIV/0!
Wed | 2024-11-06 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-06 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-06 | 16 | 0 | 19.6993 | 2024-11-06 | -174 | 32 | 2024-11-06 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2.1333 | -1.0667 |  | 0 | 0 | 0 | 2024-11-06 | 7.5882 | 12.8235 | #DIV/0!
Thu | 2024-11-07 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-07 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-07 | 16 | 0 | 19.6993 | 2024-11-07 | -190 | 32 | 2024-11-07 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -2 | -1 |  | 0 | 0 | 0 | 2024-11-07 | 7.5882 | 12.8235 | #DIV/0!
Fri | 2024-11-08 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-08 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-08 | 16 | 0 | 19.6993 | 2024-11-08 | -206 | 32 | 2024-11-08 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.8824 | -0.94118 |  | 0 | 0 | 0 | 2024-11-08 | 7.5882 | 12.8235 | #DIV/0!
Sat | 2024-11-09 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-09 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-09 | 0 | 0 | 19.6993 | 2024-11-09 | -206 | 32 | 2024-11-09 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.8824 | -0.94118 |  | 0 | 0 | 0 | 2024-11-09 | 7.5882 | 12.8235 | #DIV/0!
Sun | 2024-11-10 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-10 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-10 | 0 | 0 | 19.6993 | 2024-11-10 | -206 | 32 | 2024-11-10 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.8824 | -0.94118 |  | 0 | 0 | 0 | 2024-11-10 | 7.5882 | 12.8235 | #DIV/0!
Mon | 2024-11-11 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-11 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-11 | 16 | 0 | 19.6993 | 2024-11-11 | -222 | 32 | 2024-11-11 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.7778 | -0.88889 |  | 0 | 0 | 0 | 2024-11-11 | 7.5882 | 12.8235 | #DIV/0!
Tue | 2024-11-12 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-12 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-12 | 16 | 0 | 19.6993 | 2024-11-12 | -238 | 32 | 2024-11-12 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.6842 | -0.84211 |  | 0 | 0 | 0 | 2024-11-12 | 7.5882 | 12.8235 | #DIV/0!
Wed | 2024-11-13 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-13 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-13 | 16 | 0 | 19.6993 | 2024-11-13 | -254 | 32 | 2024-11-13 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.6 | -0.8 |  | 0 | 0 | 0 | 2024-11-13 | 7.5882 | 12.8235 | #DIV/0!
Thu | 2024-11-14 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-14 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-14 | 16 | 0 | 19.6993 | 2024-11-14 | -270 | 32 | 2024-11-14 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.5238 | -0.7619 |  | 0 | 0 | 0 | 2024-11-14 | 7.5882 | 12.8235 | #DIV/0!
Fri | 2024-11-15 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-15 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-15 | 16 | 0 | 19.6993 | 2024-11-15 | -286 | 32 | 2024-11-15 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.4545 | -0.72727 |  | 0 | 0 | 0 | 2024-11-15 | 7.5882 | 12.8235 | #DIV/0!
Sat | 2024-11-16 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-16 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-16 | 0 | 0 | 19.6993 | 2024-11-16 | -286 | 32 | 2024-11-16 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.4545 | -0.72727 |  | 0 | 0 | 0 | 2024-11-16 | 7.5882 | 12.8235 | #DIV/0!
Sun | 2024-11-17 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-17 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-17 | 0 | 0 | 19.6993 | 2024-11-17 | -286 | 32 | 2024-11-17 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.4545 | -0.72727 |  | 0 | 0 | 0 | 2024-11-17 | 7.5882 | 12.8235 | #DIV/0!
Mon | 2024-11-18 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-18 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-18 | 16 | 0 | 19.6993 | 2024-11-18 | -302 | 32 | 2024-11-18 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.3913 | -0.69565 |  | 0 | 0 | 0 | 2024-11-18 | 7.5882 | 12.8235 | #DIV/0!
Tue | 2024-11-19 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-19 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-19 | 16 | 0 | 19.6993 | 2024-11-19 | -318 | 32 | 2024-11-19 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.3333 | -0.66667 |  | 0 | 0 | 0 | 2024-11-19 | 7.5882 | 12.8235 | #DIV/0!
Wed | 2024-11-20 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-20 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-20 | 16 | 0 | 19.6993 | 2024-11-20 | -334 | 32 | 2024-11-20 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.28 | -0.64 |  | 0 | 0 | 0 | 2024-11-20 | 7.5882 | 12.8235 | #DIV/0!
Thu | 2024-11-21 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-21 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-21 | 16 | 0 | 19.6993 | 2024-11-21 | -350 | 32 | 2024-11-21 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.2308 | -0.61538 |  | 0 | 0 | 0 | 2024-11-21 | 7.5882 | 12.8235 | #DIV/0!
Fri | 2024-11-22 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-22 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-22 | 16 | 0 | 19.6993 | 2024-11-22 | -366 | 32 | 2024-11-22 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.1852 | -0.59259 |  | 0 | 0 | 0 | 2024-11-22 | 7.5882 | 12.8235 | #DIV/0!
Sat | 2024-11-23 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-23 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-23 | 0 | 0 | 19.6993 | 2024-11-23 | -366 | 32 | 2024-11-23 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.1852 | -0.59259 |  | 0 | 0 | 0 | 2024-11-23 | 7.5882 | 12.8235 | #DIV/0!
Sun | 2024-11-24 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-24 | 0 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-24 | 0 | 0 | 19.6993 | 2024-11-24 | -366 | 32 | 2024-11-24 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.1852 | -0.59259 |  | 0 | 0 | 0 | 2024-11-24 | 7.5882 | 12.8235 | #DIV/0!
Mon | 2024-11-25 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-25 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-25 | 16 | 0 | 19.6993 | 2024-11-25 | -382 | 32 | 2024-11-25 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.1429 | -0.57143 |  | 0 | 0 | 0 | 2024-11-25 | 7.5882 | 12.8235 | #DIV/0!
Tue | 2024-11-26 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-26 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-26 | 16 | 0 | 19.6993 | 2024-11-26 | -398 | 32 | 2024-11-26 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.1034 | -0.55172 |  | 0 | 0 | 0 | 2024-11-26 | 7.5882 | 12.8235 | #DIV/0!
Wed | 2024-11-27 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | -8 | -8 | 0 | 2024-11-27 | 1 | 0 | 0 | 0 | 8 | 7.5882 | 12.1111 | #DIV/0! | 2024-11-27 | 16 | 0 | 19.6993 | 2024-11-27 | -414 | 32 | 2024-11-27 | 0 | #DIV/0! | 0 | 2024-11-16 04:48 | -1.0667 | -0.53333 |  | 0 | 0 | 0 | 2024-11-27 | 7.5882 | 12.8235 | #DIV/0!
Thu | 2024-11-28 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-11-28 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-11-28 | 16 | 0 | 0 | 2024-11-28 | -430 |  | 2024-11-28 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-11-28
Fri | 2024-11-29 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-11-29 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-11-29 | 16 | 0 | 0 | 2024-11-29 | -446 |  | 2024-11-29 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-11-29
Sat | 2024-11-30 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-30 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-11-30 | 0 | 0 | 0 | 2024-11-30 | -446 |  | 2024-11-30 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-11-30
Sun | 2024-12-01 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-01 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-01 | 0 | 0 | 0 | 2024-12-01 | -446 |  | 2024-12-01 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-01
Mon | 2024-12-02 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-02 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-02 | 16 | 0 | 0 | 2024-12-02 | -462 |  | 2024-12-02 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-02
Tue | 2024-12-03 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-03 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-03 | 16 | 0 | 0 | 2024-12-03 | -478 |  | 2024-12-03 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-03
Wed | 2024-12-04 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-04 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-04 | 16 | 0 | 0 | 2024-12-04 | -494 |  | 2024-12-04 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-04
Thu | 2024-12-05 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-05 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-05 | 16 | 0 | 0 | 2024-12-05 | -510 |  | 2024-12-05 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-05
Fri | 2024-12-06 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-06 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-06 | 16 | 0 | 0 | 2024-12-06 | -526 |  | 2024-12-06 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-06
Sat | 2024-12-07 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-07 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-07 | 0 | 0 | 0 | 2024-12-07 | -526 |  | 2024-12-07 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-07
Sun | 2024-12-08 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-08 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-08 | 0 | 0 | 0 | 2024-12-08 | -526 |  | 2024-12-08 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-08
Mon | 2024-12-09 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-09 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-09 | 0 | 0 | 0 | 2024-12-09 | -526 |  | 2024-12-09 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-09
Tue | 2024-12-10 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-10 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-10 | 16 | 0 | 0 | 2024-12-10 | -542 |  | 2024-12-10 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-10
Wed | 2024-12-11 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-11 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-11 | 16 | 0 | 0 | 2024-12-11 | -558 |  | 2024-12-11 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-11
Thu | 2024-12-12 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-12 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-12 | 16 | 0 | 0 | 2024-12-12 | -574 |  | 2024-12-12 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-12
Fri | 2024-12-13 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-13 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-13 | 16 | 0 | 0 | 2024-12-13 | -590 |  | 2024-12-13 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-13
Sat | 2024-12-14 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-14 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-14 | 0 | 0 | 0 | 2024-12-14 | -590 |  | 2024-12-14 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-14
Sun | 2024-12-15 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-15 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-15 | 0 | 0 | 0 | 2024-12-15 | -590 |  | 2024-12-15 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-15
Mon | 2024-12-16 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-16 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-16 | 16 | 0 | 0 | 2024-12-16 | -606 |  | 2024-12-16 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-16
Tue | 2024-12-17 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-17 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-17 | 16 | 0 | 0 | 2024-12-17 | -622 |  | 2024-12-17 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-17
Wed | 2024-12-18 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-18 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-18 | 16 | 0 | 0 | 2024-12-18 | -638 |  | 2024-12-18 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-18
Thu | 2024-12-19 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-19 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-19 | 16 | 0 | 0 | 2024-12-19 | -654 |  | 2024-12-19 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-19
Fri | 2024-12-20 | 1 |  |  |  | 1 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 2024-12-20 | 1 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-20 | 16 | 0 | 0 | 2024-12-20 | -670 |  | 2024-12-20 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-20
Sat | 2024-12-21 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-21 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-21 | 0 | 0 | 0 | 2024-12-21 | -670 |  | 2024-12-21 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-21
Sun | 2024-12-22 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-22 | 0 | 0 | 0 | 0 | 8 |  |  |  | 2024-12-22 | 0 | 0 | 0 | 2024-12-22 | -670 |  | 2024-12-22 | 0 | 0 | 0 | 2024-11-16 04:48 | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 2024-12-22
Formulas:
Kamau = IF([Date]>TODAY(),0,[knjuguna(Kamau Njuguna)]-[Kamau])
Manoj = IF([Date]>TODAY(),0,[mkalra(Manoj Kalra)]-[Manoj])
Leonard = IF([Date]>TODAY(),0,[ljarillas(Leonard Jarillas)]-[Leonard])
Date = [Date]
Date = [Date, row above]+1
knjuguna(Kamau Njuguna) = IF([Date]>TODAY(),"",SUM(V3:[knjuguna(Kamau Njuguna)])/SUM(D3:[Kamau]))
knjuguna(Kamau Njuguna) = IF([Date]>TODAY(),"",SUM(V3:[knjuguna(Kamau Njuguna)])/SUM(AV3:[Kamau]))
mkalra(Manoj Kalra) = IF([Date]>TODAY(),"",SUM(W3:[mkalra(Manoj Kalra)])/SUM(E3:[Manoj]))
mkalra(Manoj Kalra) = IF([Date]>TODAY(),"",SUM(W3:[mkalra(Manoj Kalra)])/SUM(AW3:[Manoj]))
ljarillas(Leonard Jarillas) = IF([Date]>TODAY(),"",SUM(X3:[ljarillas(Leonard Jarillas)])/SUM(F3:[Leonard]))
ljarillas(Leonard Jarillas) = IF([Date]>TODAY(),"",SUM(X3:[ljarillas(Leonard Jarillas)])/SUM(AX3:[Leonard]))
Needed velocity = [Actual]/(NETWORKDAYS([Date],AU1,Days!$A11:A25)-1)
Actual = IF([Date]>TODAY(),"",[Actual, row above]-[Actual])
Projected Finish = IF(ISERROR([Date]+([Actual]/AN7)*(7/5)),[Projected Finish, row above],([Date]+([Actual]/AN7)*(7/5)))
Note on C2: Jarillas, Leonard: Not Weekend or Holiday
Note on AF2: Jarillas, Leonard: This does not include LJ's tests because it is messing up the projected finish date.