Production Deployment Plan

Meter NIC Firmware 5.4.53 and 5.4.33

Document Control

| CR / Project Number: |  |
| --- | --- |
| Version No: | 1.0 |
| Created On: | 23/01/2025 |
| Last Updated: | 17/02/2025 |
| Status: | FINAL |
| Author/s: | Percy Ahangama Arachchige |

Approval Status

| Stakeholder Role | Stakeholder Name | Signature | Date |
| --- | --- | --- | --- |
| Network Intelligence Manager | Tobie DeVilliers |  |  |
| Communications Manager | Stuart Bannister |  |  |
| Meter Asset Manager | Goutham Lingam |  |  |
| IOT System Service Lead | Wilton Gao |  |  |
| Market & Meter Data Manager Jac | Jack Friel |  |  |
| Manager Communication Networks Quality | Leonard Jarillas |  |  |

Document Purpose

The purpose of the Deployment Plan is to specify the business and technical resources, system requirements, steps and schedule for deployment. This document establishes the Go / No-Go criteria and the documentation requirements and gives final approval to go ahead as planned.

Related Documents

This section will list related documents. Please note that if this document is updated these related documents may also need to be changed.

| Document | Location | Relationship |
| --- | --- | --- |
| NIC Firmware_TSR_5.4.XX3_v1.0 – Test Summary Report |  | TSR |

Reviewers

List the relevant reviewers who are responsible for the deliverables defined in this document.

| Reviewer Title | Reviewer Name | Reviewed (Yes/No) |
| --- | --- | --- |
| Metering Engineer • United Energy | Karl Ngo | Reviewed |
| Senior AMI Strategy Engineer • United Energy | Graeme Watson | Reviewed |
| AMI Communications Analyst • Network | Sangsukdee, Wayne | Reviewed |
| Communication Networks Laboratory Techni • Network | Njuguna, Kamau | Reviewed |
| AMI Communications Analyst • United Energy | Cherian, Jogy | Reviewed |

Document Distribution (Information only)

| Distributed to |  |
| --- | --- |

Table of Contents

1.	Introduction	4

1.1.	Project Background	4

1.2.	Objectives	4

1.3.	Dependencies	4

2.	Deployment Approach	5

2.1.	Scope	5

2.2.	Deployment Schedule and Stages	6

2.2.1.	Deployment Schedule	6

2.2.2.	Deployment Stages	8

1.	Pre-analysis Stage	9

2.	BVT Stage (50 Meters)	9

3.	Stage 1 (100 Meters)	10

4.	Stage 2 (500 meters)	12

5.	Stage 3 (All meters)	13

6.	BAU Stage (All remaining Meters)	14

3.	Deployment Roles and Responsibilities	17

3.1.	Deployment Lead	17

3.2.	Go – No Go	17

3.3.	Escalation	17

3.4.	Stakeholder Communication	17

3.5.	Operational and Support Groups	18

4.	Identified Risks	19

5.	Appendix	20

5.1.	FWU Progress Report	20

6.	Revision	21

# Introduction

## Project Background

To address existing defects in NIC Architecture (AKIO/RNI), Itron has released NIC firmware version 5.4.x3. This updated firmware is intended to resolve the identified issues and will be used to upgrade production U1300/U3400 meters currently running NIC firmware versions 4.8.2C (RNI) and 3.12.9c (AKIO).

Before deploying NIC firmware 5.4.53 (RNI) and 5.4.33 (AKIO) to the production AMI system, it is essential to ensure that the new release poses minimal risk to business operations and meets all relevant requirements. To this end, the Communication Networks Quality Group has conducted rigorous testing to verify the firmware's functionality and performance.

Note: The NIC Firmware release (5.4.13) for ARM architecture is not part of this testing and deployment. It will be tested and deployed in near future separately.

## Objectives

- Upgrade all U1300 and U3400 meters NIC firmware  to 5.4.53 (NIC 5/RNI)

- Upgarde all U1300 and U3400 meters NIC Firmware to 5.4.33 (NIC 3 and NIC 4 / AKIO)

## Dependencies

- NIC Firmware_TSR_5.4.XX3_v1.0 – Test Summary Report

# Deployment Approach

## Scope

- Both UE and VPN AMI network and devices are in scope.

- Meters with the following properties will be in scope of this deployment activity.

| Device Type | Device Sub Type | NIC Architecture | Currently running NIC Firmware | New NIC firmware |
| --- | --- | --- | --- | --- |
| Meter | L+G IEC U1300 1PH 1E HAN | AKIO | 3.12.9c | 5.4.33 |
|  | L+G IEC U1300 1PH 1E LC HAN |  |  |  |
|  | L+G IEC U1300 1PH 2E LC HAN |  |  |  |
|  | L+G IEC U3400 3PH DIR CONN HAN |  |  |  |
|  | L+G IEC U3400 3PH DIR CONN LC HAN |  |  |  |
|  | L+G IEC U1300 1PH 1E HAN | RNI | 4.8.2c | 5.4.53 |
|  | L+G IEC U1300 1PH 1E LC HAN |  |  |  |
|  | L+G IEC U1300 1PH 2E LC HAN |  |  |  |
|  | L+G IEC U3400 3PH DIR CONN HAN |  |  |  |
|  | L+G IEC U3400 3PH DIR CONN LC HAN |  |  |  |

Table 1: Device Firmware in Scope

- Please find below list of each meter count based on NIC Architecture

| Device Sub Type | NIC Architecture | Currently running NIC Firmware | Count of Device |
| --- | --- | --- | --- |
| L+G IEC U1300 1PH 1E HAN | AKIO | 3.12.9c | 143502 |
| L+G IEC U1300 1PH 1E LC HAN |  |  |  |
| L+G IEC U1300 1PH 2E LC HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN LC HAN |  |  |  |
| L+G IEC U1300 1PH 1E HAN | RNI | 4.8.2c | 53905 |
| L+G IEC U1300 1PH 1E LC HAN |  |  |  |
| L+G IEC U1300 1PH 2E LC HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN LC HAN |  |  |  |

Table 2: VPN Meters in Scope

| Device Sub Type | NIC Architecture | Currently running NIC Firmware | Count of Device |
| --- | --- | --- | --- |
| L+G IEC U1300 1PH 1E HAN | AKIO |  | 0 |
| L+G IEC U1300 1PH 1E LC HAN |  |  |  |
| L+G IEC U1300 1PH 2E LC HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN LC HAN |  |  |  |
| L+G IEC U1300 1PH 1E HAN | RNI | 4.8.2c | 20022 |
| L+G IEC U1300 1PH 1E LC HAN |  |  |  |
| L+G IEC U1300 1PH 2E LC HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN HAN |  |  |  |
| L+G IEC U3400 3PH DIR CONN LC HAN |  |  |  |

Table 3: UE Meters in Scope

## Deployment Schedule and Stages

The upgrade shall be divided into several stages as shown in the figure below.

Note: The mentioned deployment schedule for different stages will be followed for each NIC Firmware separately, once for NIC 5.4.33 and once for 5.4.53.

Deployment Schedule

The proposed deployment schedule is shown in the figure below in reference to the start date of  3rd of Feb 2025. This start date is dependent on the approval of the deployment plan (this document) The duration are estimates based on previous Nic firmware upgrades and will be monitored and adjusted during the deployment activity.

Figure 1- Deployment Schedule

Deployment Stages

The BVT upgrade of the meters should be carried out in well-established areas, preferably in proximity to the Roony Depot or Brooklyn Depot.

Example: Sunshine City

The upgrade shall be divided into several stages as shown in the figure below:

BVT

(50 Meters)

Stage 1

(100 Meters)

Stage 2

(500 Meters)

Stage 3

(All remaining Meters)

BAU

(All Meters)

Pre-analysis

- Identify meters for BVT, Stage 1 and Stage 2

- Upgrade to 10 Meters

- Check if any Meter performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to 100 Meters

- Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to 500 Meters

- Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to all Meters.

- BAU process Check if any AP performances /malfunctions is introduced due to firmware upgrade.

- Upgrade to remaining  Meters

- BAU process Check if any meter performances /malfunctions is introduced due to firmware upgrade.

Figure 2 - Firmware deployment stages

Progress of the firmware upgrade shall be monitored through the FWU reporting tool and FWU project details.

### Pre-analysis Stage

Resources Required: ACCG

The pre-analysis stage shall be composed of the following activities:

- Identify Meters with operational state “Active” and Disconnected” having good communication history and avoid using COMMS_FLAPPERS

- List all meters that are to be in scope of BVT, Stage 1 and Stage 2 based on the following criteria:

  - Operation state : Active

  - Location : Close proximity to Burnly depot or Brooklyn depot

  - BVT Stage : 50 Meters (U1300/U3400) Nic Architecture AKIO/RNI

  - Stage 1: 100 Meters (U1300/U3400) Nic Architecture AKIO/RNI

  - Stage 2: 500 Meters (U1300/U3400) Nic Architecture AKIO/RNI

- Import list of meters BVT,Stage 1 and Stage 2 into the tracking spreadsheet located in:

ACC Deployment\2025 - Meter NIC Firmware Deployment

- Collect all pre upgrade data and record in the tracking spreadsheet. The pre and post firmware upgrade data shall be compared to ensure that the expected behaviour is observed.

| Data to be collected | Method | Expected |
| --- | --- | --- |
| Meter communication | UIQ Ping Schedule/NC/MKT | Meters have >99% comms performance |
| Meter Interval data Read | UIQ Schedule/NC | Meter data up to date available |
| Meter events | UIQ Schedule | There are no unexpected meter events generated |
| Meter Performance | UIQ Schedule | Hourly meter read performance as expected |

Table 4 - Pre & Post Upgrade Data

### BVT Stage (50 Meters)

Resources Required: ACCG, UIQ Support, Data Analytics, AMI Data (MDP)

During the BVT stage, a small number (50) of meters shall be upgraded and the impact of the upgrade analyzed. This minimises the the risk of meter malfunctions, if any, that may be introduced by the new firmware that has not been detected during testing.

Steps:

  - Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

  - Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past NIC firmware upgrades.

  - Collect all post upgrade data and record in the tracking spreadsheet.

  - Compare the pre and post upgrade data in the tracking spreadsheet and verify the impact of the deployment of new firmware to the Meter  performance.

  - Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major adverse effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

  - If all issues, if any, has been resolved, proceed to the next stage.

  - Communicate results of the BVT, and if proceeding to the next stage, to the relevant stakeholders.

### Stage 1 (100 Meters)

Resources Required: ACCG, UIQ Support or Data Analytics

In Stage 1, a larger number (100) of meters shall be upgraded and the impact of the upgrade analyzed.

Steps:

- Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

- Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past NIC firmware upgrades.

- Monitor for any meter failed the upgrade and send a list to the Communication Networks Quality Manager for investigation and triage.

- Collect all post upgrade data and record in the tracking spreadsheet.

- Compare the pre and post upgrade data in the tracking spreadsheet and verify the impact of the deployment of new firmware to the Meter performance.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- If all issues, if any, has been resolved, proceed to the next stage.

- Communicate results of the Stage 1, and if proceeding to the next stage, to the relevant stakeholders.

### Stage 2 (500 meters)

Resources Required: ACCG, UIQ Support or Data Analytics

In Stage 2, a significant number (500) of meters shall be upgraded and the impact of the upgrade analyzed.

Steps:

- Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

- Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past NIC firmware upgrades. If necessary, restart the FWU project.

- Monitor for any meter that failed the upgrade and send a list to the Communication Networks Quality Manager for investigation and triage.

- Collect all post upgrade data and record in the tracking spreadsheet.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- If all issues, if any, has been resolved, proceed to the next stage.

- Communicate results of Stage 2, and if proceeding to the next stage, to the relevant stakeholders.

### Stage 3 (All meters)

Resources Required: ACCG, UIQ Support or Data Analytics

In Stage 3, there is now high confidence that the new firmware does not pose any significant risk to the meter functionality. All the remaining meters that needs to be upgraded to the new firmware will be covered in this stage.

Steps:

- Create and run the FWU project for each firmware image type. The upgrade setting for each FWU upgrade shall be as follows:

- Monitor the success rate and duration of each firmware upgrade. Report any noticeable slowness in the upgrade compared to past NIC firmware upgrades. If necessary, restart the FWU project.

- Monitor for meters that failed the upgrade and send a list to the Communication Networks Quality Manager for investigation and triage.

- Collect all post upgrade data and record in the tracking spreadsheet.

- Compare the pre and post upgrade data in the tracking spreadsheet and verify the impact of the deployment of new firmware to the meter performance.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- If all issues, if any, has been resolved, proceed to the next stage.

- Communicate results of Stage 3, and if proceeding to the next stage, to the relevant stakeholders.

### BAU Stage (All remaining Meters)

Resources Required: ACCG, UIQ Support or Data Analytics

In the BAU stage, all the remaining meters shall be targeted and upgraded to the New firmware.

Steps:

- Create the FWU audit for each NIC Architecture type. The suggested audit setting for each FWU audit shall be as follows:

Device Group settings

- Notify relevant stakeholders prior to commencement of the audit and automatic upgrade. UIQ Support team will need to monitor the backend system and UIQ application during the upgrade.

- Monitor the success rate and duration of each automatic firmware upgrade daily. Report any noticeable slowness in the upgrade compared to past NIC firmware upgrades. If necessary, restart the FWU project.

- Continue to monitor the events and look for any critical events, not limited to those listed below.

- Check for any communications from UIQ Support, Data Analytics and AMI Data team for any major impact. If any major effect is detected in this stage, stop the deployment and escalate to the Communication Networks Quality Manager. The issue will be investigated further with assistance from the following teams:

- Communication Networks Quality

- Other teams as needed

- Continue to monitor the upgrade success rate, critical events.

- Communicate firmware upgrade progress and any issues to relevant stakeholders.

# Deployment Roles and Responsibilities

## Deployment Lead

The deployment lead for the new nic firmware are:

- VPN: Percy Arachchige

- UE: Jogy Cherian

## Go – No Go

Each stage will have a go-no go checkpoint with the following stakeholders as approvers:

| Deployment Stage | Role | Stakeholder |
| --- | --- | --- |
| Stage 1 Stage 2 | Metering Engineer • United Energy | Karl Ngo |
|  | Senior AMI Strategy Engineer • United Energy | Graeme Watson |
|  | AMI Communications Analyst • Network | Sangsukdee, Wayne |
|  | Communication Networks Laboratory Techni • Network | Njuguna, Kamau |
|  | AMI Communications Analyst • United Energy | Cherian, Jogy |
| Stage 3 BAU Upgrade |  |  |
|  | Communications Manager | Stuart Bannister |
|  | Meter Asset Manager | Goutham Lingan |
|  | IOT System Service Lead | Wilton Gao |
|  | Market & Meter Data Manager Jac | Jack Friel |
|  | Manager Communication Networks Quality | Leonard Jarillas |

## Escalation

The first point of escalation will be the Communication Netwoworks Quality Manager and depending on the issue, he/she will contact the relevant stakeholders in the reviewer’s list.

## Stakeholder Communication

The stakeholders in the reviewer and approver list shall be notified of the progress and any issue found during the firmware upgrade deployment. The mode of communication shall be via email.

## Operational and Support Groups

- List the support to be provided for the deployment and post go live.  For example, what role is the service desk playing and have they been informed.  Will the Business team provide trained floor walkers on go live day?

- ACCG

  - Overall firmware upgrade process

  - Send progress report

- UIQ Support

  - General UIQ application support and monitoring

  - Support on data requests that can’t be easily retrieve from the UI

- Data Analytics

  - SIQ and PQ polling data monitoring

  - Support on data requests that can’t be easily retrieve from the UI

- AMI Data (MDP)

  - AMI data to market monitoring

Complete the table below, listing all required resources for the deployment.

# Identified Risks

| Ref | Description | Details | Mitigation |
| --- | --- | --- | --- |
| Risk#1 | Undesired meter functionality due to new NIC firmware | Meter stops functioning correctly resulting loss of functionality | - Critical tests have been done during testing. - Staged deployment of the NIC firmware. - Revert the firmware to the previous version |
| Risk#2 |  |  |  |

# Appendix

Include exports from ALM for the execution results and defects.

## FWU Progress Report

The following information shall be sent as part of the daily FWU progress report.

| Issue# | Summary | Status |
| --- | --- | --- |

| Project Name | Start | Stop | Total Devices | Succeeded | Failed | % completed |
| --- | --- | --- | --- | --- | --- | --- |

# Revision

| Version | Date | Updated by | Comments |
| --- | --- | --- | --- |
| 0.1 | 23 January 2025 | PA | Draft |
| 1.0 | 17 February 2025 | LJ | Final |