## Sheet1
Meter Type | Device Sub Type | NIC Architecture | Currently running NIC Firmware | New NIC firmware
L+G | L+G IEC U1300 1PH 1E HAN | AKIO | 3.12.9c | 5.4.53
L+G IEC U1300 1PH 1E LC HAN
L+G IEC U1300 1PH 2E LC HAN
L+G IEC U3400 3PH DIR CONN HAN
L+G IEC U3400 3PH DIR CONN LC HAN
| L+G IEC U1300 1PH 1E HAN | RNI | 4.8.2c | 5.4.53
L+G IEC U1300 1PH 1E LC HAN
L+G IEC U1300 1PH 2E LC HAN
L+G IEC U3400 3PH DIR CONN HAN
L+G IEC U3400 3PH DIR CONN LC HAN
Meter Type | Device Sub Type | NIC Architecture | Currently running NIC Firmware | New NIC firmware
L+G | L+G IEC U1200 1PH 1E HAN | ARM | 3.12.9 | 5.4.13
L+G IEC U3300 3PH DIR CONN HAN
L+G IEC U3300 3PH DIR CONN LC HAN
| L+G IEC U1200 1PH 1E LC HAN | AKIO | 3.12.9c | 5.4.33
L+G IEC U1200 1PH 2E LC HAN L+G IEC U3300 3PH DIR CONN HAN
L+G IEC U3300 3PH DIR CONN LC HAN
L+G IEC U3350 3PH CT CONN
Meter Type | Device Sub Type | Meter Firmware | Currently running NIC Firmware | NIC Firmware
Secure DPI Sprint 210 | Secure DPI Sprint 210 DLMS/COSEM RD 1E 1LC | FPGCG01 | 5.4.5 | 5.4.53
Secure DPI Sprint 210 DLMS/COSEM RD 1E 2LC
Secure DPI iCredit 510 | Secure DPI iCredit 510 DLMS/COSEM RD 1E 1LC | FPH7G01 | 5.4.5 | 5.4.53
Secure DPI iCredit 510 DLMS/COSEM RD 1E 2LC
Secure DPI iCredit 510 DLMS/COSEM RD 2E 2LC
Secure DPI Premier 210 | Secure DPI Premier 210 DLMS/COSEM 1E 1LC | FPGDG01 | 5.4.5 | 5.4.53

## Sheet2
| WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9
NIC Architecture - AKIO/ARM | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29
Meter Firmwate Deployment
Pilot (10 meters)
BVT Upgarde (#50)
Post BVT Analysis
Go/No Go | bar: 2025-08-11
Stage 1 Upgarde (#100)
Post Stage 1 Analysis | bar: 2025-08-11
Go/No Go
Stage 2 Upgarde (#500)
Post Stage 2 Analysis | bar: 2025-08-18
Go/No Go
BAU Upgrade (Via FU Audits)
Post BVT Analysis
Go/No Go
NIC Architecture -RNI
Meter Firmwate Deployment
Pilot (10 meters) | bar: 2025-09-08
BVT Upgarde (#50)
Post BVT Analysis | bar: 2025-09-08
Go/No Go
Stage 1 Upgarde (#100)
Post Stage 1 Analysis | bar: 2025-09-15
Go/No Go
Stage 2 Upgarde (#500)
Post Stage 2 Analysis
Go/No Go
BAU Upgrade (Via FU Audits)
Post BVT Analysis
Go/No Go