# Calendar:

## Change Working Time

Go to Project-> Change Working Time: It gives the calendar popup option.

Three available Calendar options. If you want custom calendar, then select Create New Calendar.

This New Calendar can be set as Project calendar by:

Project-> Project Information-> Calendar

# View:

Represents the information in different ways, don’t manipulate the information.

# Module 6:

Duration and Work Formula:

## Duration:

The length of the task from start to End.

## Work:

Person hours required to finish the task.

## Units:

Percentage of resource’s available time committed to the task.

100%= 1 unit

50% = 0.5 units

One third = 0.33 unit

Duration = Work/Units

i.e.” 40 hours to finish task, for 1 resource working full time:

Duration = W/U = 40/1 = 40 hours

What if resource is available for 50%

Then Duration = 40/0.5 = 80 Hours.

# Shortcut for Task Linking:

Select the tasks, press: CTRL+F2: It will link the tasks in Finish to Start way linking.

# Summary Tasks:

On Gantt Chart is it shown by down black bracket over the list of tasks under Summary Tasks.

Select the tasks-> Go to Task menu-> select ‘Summary’

View->Outline: for expand or collapse on different level.

Format-> check box for ‘Summary Tasks’ will hide or show summary task, and only display tasks.

Format-> Project Summary Task’ : Root level Summary task , which present the entire Project, can be shown by checking the ‘Project Summary Task’ in the Format section.

Other option is by selecting the task-> Indenting/Outdenting it from Task menu. To be careful with this method

Imp:

- Directly modify the summary task duration. Gantt Chart shows the time gap or overtime by teel or red colour.

- When you remove or delete the Summary Task, all sub tasks are also deleted. But to outdent the summary task if only summary task is to be deleted.

- Can be recognized by small rectangle.

# Milestone:

- No duration of the task- make duration 0 days to convert to milestone.

- No effect on scheduling.

- Milestone are presented as diamond shape.

- Click on the task below, where you want to add milestone task. And click on Task->Milestone: it adds the milestone to the plan.

# Task Linking:

- When referencing the tasks in Predecessor section manually, task numbers are used not WBS numbers.

- Don’t link Summary Tasks and don’t assign resources or duration to summary tasks.

- Link button and Editing Predecessor are equally appropriate.

- Check no overlocation red indicators are there.

- Some tasks may have special data constraints, they have special indicator. Edit the dates manually.

# Recurring Tasks:

- Task Drop down and select recurring task, where you want to insert.

- Special icon- recurring.

- Frequent cause of over allocation- To overcome you may change the duration to 0.

- Recurring task has the high priority, so project will not delay recurring task.

- Can not convert existing task to recurring task.

# Task Formatting:

- Text Styles: Go to Format->TextStyles: Select Item to change.

# Tips:

- CTRL + N- New file open

- CTRL+O- Open existing file

- CTRL+Home- bring the cursor to very first cell